## 05-04-2022
Resource Name | Action Point / Impediments | Status | Comments
Harini R & Chitrarasu | finding solution for github account problem
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Harini R | Requirement refining and storing of lower hierarchy designated people | Work flow completed | How a user can view his lower hierarchy person on the system | 5 | 2
Chitrarasu V | Working to store the profile in database | User Story completed | How to show the lower profile in dashboard | 5 | 2
Sekhar | Requirement refining | User Workflow | How can store lower hierarchy on the system. | 5 | 2
Nagaraj K | Hierarchy Mapping | Workflow based on Filters | how to map the lower profiles under higher profiles | 5 | 2
Kishore kumar A N | Requirement refining | User Workflow | How to show the lower profile in dashboard | 5 | 2
Ramakrishna | Requirements and hierachy storage | User Flow for creation | How to add restrictions | 5 | 2
Brindha M | Hierarchy Mapping | User Flow for searcher | how to map hierarchy | 5 | 2
Gugan RB | Working to store the profile in database | User Story completed,User Flow for searcher | How to show the lower profile in dashboard | 5 | 2
Yoga Dharshini | What are to be maintained as master data and role mapping | Overall flow for both user | Hierarchy mapping | 5 | 2
Dinesh Kumar

## 06-04-2022
Resource Name | Action Point / Impediments | Status | Comments
Harini R & Chitrarasu | finding solution for github account problem | Completed | Signed in another user
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Brindha | Acceptance criteria for Admin | Discussion and meeting with rafi - 1hour Team Discussion- 2hours Made minor changes in user story - 1 hour Acceptance criteria for Creator and Searcher - Completed - 2hours | Acceptance criteria for Admin | 6 | 1 | Having doubt in Share feature for acceptance criteria
Chitrarasu | Exploration on Web API Assumptions | Meeting with rafi - 1 hrs Made minor changes in user story as discussed in previous meeting - 1.5 hrs Discussion with Gugan about Assumptions - 1 hrs Discussion with Gugan about Constraints - 1.5 hrs Discussion with team on admin's user story,work flow,prototype and hierarchial mapping - 2 hrs | Assumptions | 7 | 1 | Having clarity in different assumptions was difficult
Dinesh Kumar | AB | AB | AB | AB | AB | AB
Gugan | Exploration on Entity Framework Assumptions | Meeting with rafi - 1 hrs Made minor changes in user story as discussed in previous meeting - 1.5 hrs Discussion with Chitrarasu about Assumptions - 1 hrs Discussion with Chitrarasu about Constraints - 1.5 hrs Discussion with team on admin's user story,work flow,prototype and hierarchial mapping - 2 hrs | Assumptions | 7 | 1 | Having clarity in different assumptions was difficult
Harini | Creation of prototype for entering project details in the system,View page | Requirement refining - Project Details - 1hour Prototype for Register, Entering personal details pages - 1.5 hours Made minor changes in user story as discussed in previous meeting - 1.5 hours Discussion with team and Meeting with rafi - 3hours | Share feature in protoype - holded | 7 | 1 | Having doubt in creation for prototype of share feature
Kishore | Creation of prototype for Viewing their profiles | Requirement Refining- Break information for experience -1hr Prototypes for Login,Dashboard,Objective and Skills-2hrs Meeting with Rafi-1hr Meeting with Team Regarding Work assigning-2hrs | Profile Tempalte View | 6 | 1 | not having any idea how Profile template looks like
Nagaraj | Acceptance criteria for Admin | Acceptance criteria for Creator and Searcher - 2 hours Team Discussion on MoM scoped requirements-2 hours Meeting with raffi - 1 hour Hierarchy mapping - 30 minutes | - | 5.5 | 1 | -
Ramakrishna | Creation of prototype for Viewing their profiles | Requirement Refining- Profile details-1hr,Prototypes for Register,Education,Objective and Skills-2hrs,Meeting with Rafi-1hr,Meeting with Team Regarding Work assigning and Changes-2hrs | Profile Template while downloading and view | 6 | 1 | not having any idea how Profile template looks like
Sekhar | Exploring on Entity Framework. | Discussion and meeting with rafi - 1 hrs. Minor changes in user story and workflow - 1:30 hrs. Added admin as an another user, created admin workflow - 1 hrs. Discussion with team members - 2 hrs. | profile searcher can review another user profile. | 5:30 hrs | 1:30 hrs | Whether profile searcher or admin can review others profile.
Yoga Dharshini G | Admin controls and user profile reviews | Added admin as another user,created admin user story - 1:30hrs Made minor changes in user story and work flow - 2hr Discussion with Rafi - 1:30hrs Discussion with team members and Sekhar - 1:30 hr | Admin's other controls and Profile searcher or admin should review profiles or not | 6:30 Hrs | 3 hrs | Stuck with admin's other control flow and validation or verification has to be done or not

## 07-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Brindha | Exploration on Web API | Prototype for home page - 2 hours Acceptance criteria for Admin and HR - 1 hour Meeting with Raffi - 1.5 hour Team discussion - 2 hours | - | 6.5 | 1 | Practice with Balsamiq.
Chitrarasu | Exploration on WPI | Create prototype for view the created Profile - 2hrs Meeting with rafi - 1.5hr Discussion with Team about Prototype and admin user story - 3hrs | - | 6.5 | 1 | Practice with Balsamiq.
Dinesh Kumar | AB | AB | AB | AB | AB | AB
Gugan | Exploration on Entity Framework | Meeting with Rafi - 1.5 hrs Discussion with team about Prototype and admin user story - 3 hrs Prototype for HR user creation - 30 mins Prototype for Profile searcher view - 1.5hr | sharing profile,status | 6.5 | 1 | Doubt in share feature and status feature
Harini R | Exploration on web api | Created prototype for create profile page and home page - 2.5hrs Meeting with rafi - 1.5hr Discussion with Team about Prototype and admin user story - 3hrs | - | 7 | 1 | Doubt in share feature
Kishore | Entity Framework-Code first approach | Prototypes for Change Password and My profile-2hrs Meeting with Rafi-1hr Meeting with Team Regarding Work assigning-2hrs |  | 5 | 2
Nagaraj | - | Prototype for Login page - 30 mins Acceptance criteria for Admin and HR - 1 hour Meeting with Raffi - 1.5 hour Team discussion - 2.5 hours | - | 5.5 | 2 | Practiced with Balsamiq.
Ramakrishna | Entity Framework-Code first approach | Created prototypes for profile searcher view and HR user creation-2hrs,Meeting with Rafi-1.5hrs,Meeting with team regarding work assingnig and prototype designing-3hrs | sharing profile | 6.5 | 1 | Doubt in share feature and status feature
Sekhar | Exploration on Web API | Meeting with rafi - 1hr. Discussion with team member about prototype designing - 3hrs. Made changes in userstory (Creater,Searcher) & Created Admin, HR Partner userstory - 2hrs. | - | 6 | 1:30 | -
Yoga Dharshini G | Exploring prototype and Entityframework | Made changes in workflow (Creater,Searcher) & Created Admin, HR Partner workflow - 3hrs Discussion with team members - 2hrs Review with Rafi - 1:30hrs MOM updated and discussed - 1hr | Mail System | 7:30 | 2 | No clarification in mail system and share feature

## 08-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Brindha | Entity and Relationship Model | Prototype for create profile - 2 hours Meeting with raffi - 1 hour Discussion with team members- 3 hours | - | 6 | 1 | Practiced with Balsamiq.
Chitrarasu | Entity and Relationship Model | Changed prototype for view page of created Profile - 2hrs Meeting with rafi - 1hr Discussion with Team about prototype and entity and relationship model- 3hrs | - | 6 | 1 | Gained knowledge in working with Balsamiq
Dinesh Kumar | AB | AB | AB | AB | AB | AB
Gugan | Exploration on Entity Framework,Entity and Relationship model | Create prototype for view the created Profile - 2hrs Meeting with rafi - 1hr Discussion with Team about modify the prototype - 2hrs Discussion with team about entity and relationship model - 1hr | - | 6 | 1 | Practiced with Balsamiq,Have to work in entity model
Harini R | Entity and relationship model | Changed prototype for create profile page - 2hrs Meeting with rafi - 1hr Discussion with Team about Prototype and entity and relationship model - 3hrs | - | 6 | 1 | Gained knowledge in working with Balsamiq
Kishore | Entity Framework-Code first approach | Prototypes for View my profile for searcher-2hrs Meeting with Rafi-1hr Meeting with Team Regarding Work assigning-2hrs |  | 5 | 2 | -
Nagaraj | Entity and Relationship | Modified the user stories - 1.5 hours Meeting with raffi - 1 hour Discussion with team about changing prototype's profile details -2 hours | - | 4.5 | 3 | Practiced with Balsamiq.
Ramakrishna | Entity Relationship | Prototype for Login and Password changes- 2 hours Meeting with raffi - 1 hour Discussion with team members regarding prototypes - 3 hours |  | 6 | 2 | Practiced with Balsamiq.
Sekhar | Entity Relationship | Meeting with raffi - 1 hour Discussion with team members regarding prototypes - 3 hours Prototype for profile creator - 1 hour | - | 5 | 1 | Practiced with Balsamiq.
Yoga Dharshini G | Exploring prototype and Entityframework | Added Prototype for Searcher, Admin and Reporting person Homepage - 2hrs Discussion with team members - 2hrs Review with Rafi - 1hr MOM updated and discussed - 1hr | - | 6hrs | 1 | -

## 09-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Brindha | Entity and Relationship Model | Created Entity model - master data,User details,Relationship- 2 hours Meeting with raffi - 1.5 hour Discussion with Team about modify the prototype - 2 hours Discussion with team about entity and relationship model - 3 hours | - | 6.5 | 1 | Practiced with draw.io.
Chitrarasu | Entity and Relationship Model | Changed prototype for view page of created Profile - 2hrs Meeting with rafi - 1hr Discussion with Team about prototype and entity and relationship model- 3hrs | - | 6 | 1 | Gained knowledge in working with Balsamiq
Dinesh Kumar | AB | AB | AB | AB | AB | AB
Gugan | Exploration on Entity Framework,Entity and Relationship model | Created entity model - master data,User details,Relationship- 2hrs Meeting with rafi - 1.5 hr Discussion with Team about modify the prototype - 2hrs Discussion with team about entity and relationship model - 1hr | - | 6.5 | 1 | Practiced with draw.io.
Harini R | Entity and relationship model | Changed prototype for create profile page - 2hrs Meeting with rafi - 1hr Discussion with Team about Prototype and entity and relationship model - 3hrs | - | 6 | 1 | Gained knowledge in working with Balsamiq
Kishore | Entity Framework-Code first approach | Prototypes for View my profile for searcher-2hrs Meeting with Rafi-1hr Meeting with Team Regarding Work assigning-2hrs |  | 5 | 2 | -
Nagaraj | AB | AB | AB | AB | AB | AB
Ramakrishna | Entity Framework | Protypes for Login page maintained same font sizes-2hrs,meeting with Rafi-1hr,Meeting with Team Regarding Work spilting-2hrs | - | 6 | 1
Sekhar | Entity Framework | Protypes for user creation and change font size-1hrs. meeting with Rafi-1hr. Meeting with Team Regarding Work spilting-2hrs | - | 4 | 2 | Practiced with Balsamiq.
Yoga Dharshini G | Exploring prototype and Entityframework | Added Prototype for Searcher, Admin and Reporting person Homepage - 2hrs Discussion with team members - 2hrs Review with Rafi - 1hr MOM updated and discussed - 1hr | - | 6hrs | 1 | -

## 11-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Brindha | Entity and Relationship Model | Created Entity model - master data,User details,Relationship- 2 hours Meeting with raffi - 1.5 hour Discussion with Team about modify the prototype - 2 hours Discussion with team about entity and relationship model - 3 hours | - | 6.5 | 1 | Practiced with draw.io.
Chitrarasu | Entity and Relationship Model | Changed prototype for view page of created Profile,Admin & HR home page - 2hrs Meeting with rafi - 1.5hr Discussion with Team about prototype and entity and relationship model- 3hrs | - | 6.5 | 1 | Gained knowledge in working with Balsamiq
Dinesh Kumar | AB | AB | AB | AB | AB | AB
Gugan | Exploration on Entity Framework,Entity and Relationship model | Created entity model - master data,User details,Relationship- 2hrs Meeting with rafi - 1.5 hr Discussion with Team about modify the prototype - 2hrs Discussion with team about entity and relationship model - 1hr | - | 6.5 | 1 | Practiced with draw.io.
Harini R | Entity and relationship model | Changed prototype for create profile page - 2hrs Meeting with rafi - 1hr Discussion with Team about Prototype and entity and relationship model - 3hrs | - | 6 | 1 | Gained knowledge in working with Balsamiq
Kishore | Entity Framework-Code first approach | Prototype for Profile history and Profile view- 2hrs. Meeting with rafi - 1.5 hr Discussion with Team about modify the prototype - 2hrs Discussion with Team about prototype and entity and relationship model- 1hrs | - | 6.5 | 1 | Gained knowledge in working with Balsamiq
Nagaraj | AB | AB | AB | AB | AB | AB
Ramakrishna | Entity Framework-Code first approach | AB | - | - | - | -
Sekhar | AB | AB | AB | AB | AB | AB
Yoga Dharshini G | Exploring prototype and Entity | Modified Prototype Homepage- 2hrs Discussion with team members - 2hrs Project Review with Rafi - 1hr MOM updated and discussed - 1hr | - | 6hrs | 1 | -

## 12-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Brindha | Entity and Relationship Model | Modified Entity model - master data,User details,Relationship,Data entries in excel - 2 hours Meeting with raffi - 1.5 hour Discussion with Team about entity and prototype-3 hours | - | 6.5 | 1 | Practiced with draw.io.
Chitrarasu | Entity and Relationship Model | Changed prototype for view page of created Profile,Admin & HR home page - 2hrs Meeting with rafi - 1.5hr Discussion with Team about entity and relationship model- 2hrs | - | 5.5 | 1 | Gained knowledge in working with Balsamiq
Dinesh Kumar | AB | AB | AB | AB | AB | AB
Gugan | Exploration on Entity Framework,Entity and Relationship model | Created entity model - master data,User details,Relationship- 2hrs Meeting with rafi - 1.5 hr Discussion with team about entity and relationship model - 2hr | - | 5.5 | 1 | Practiced with draw.io.
Harini R | Entity and relationship model | Changed prototype for create profile page and home page - 2hrs Meeting with rafi - 1.5hr Discussion with Team about entity and relationship model - 2hrs | - | 5.5 | 1 | Gained knowledge in working with Balsamiq
Kishore | Entity Framework-Code first approach | Changed Prototype for Searcher Home Page- 1hrs. Created the prototype for Total Number of User and Approved user-2hrs Meeting with rafi - 1.5hr Discussion with Team about modify entity and relationship model- 2hrs | - | 6.5 | 1 | Gained knowledge in working with Balsamiq
Nagaraj | Entity and Relationship Model | Created entity model - master data,User details,Relationship- 2hrs Meeting with rafi - 1.5 hr Discussion with team about entity and relationship model - 2hr | - | 2 | 2 | -
Ramakrishna | Entity and Relationship Model | Modified Entity model - master data,User details,Relationship,Data entries in excel - 2 hours Meeting with raffi - 1.5 hour Discussion with Team about entity and prototype-3 hours | - | 6.5 | 1 | Practiced with draw.io.
Sekhar | Entity Framework-Code first approach | Meeting with rafi - 1.5 hr, Discussion with Team about prototype and entity and relationship model- 2 hrs, Creating for entity tables in draw.io - 2hrs, Modified for user creation in prototype - 1hr | - | 6.5 | 1 | Practiced with draw.io.
Yoga Dharshini G | Exploring prototype and Entity | Modified Prototype of Homepage- 1hrs Discussed entities and relationship with team members - 2hrs Project Review with Rafi - 1.5hr MOM updated and discussed - 1hr | - | 5.5hrs | 1 | -

## 13-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Brindha | Entity and Relationship Model | Modified Entity model - Relationship - 2 hours Meeting with raffi - 1.5 hour Discussion with Team about entity and prototype-2 hours | - | 5.5 | 1 | Practiced with draw.io.
Chitrarasu | Entity and Relationship Model | Changed grid to box method in profile creation details and user under me tab included in prototype - 2hrs Meeting with rafi - 1.5hr Discussion with Team about entity and relationship model- 2hrs | - | 5.5 | 1 | Gained knowledge in working with Balsamiq
Dinesh Kumar | AB | AB | AB | AB | AB | AB
Gugan | Entity and Relationship Model | Modified Entity model - Relationship - 2 hours Meeting with raffi - 1.5 hour Discussion with Team about entity and prototype-2 hours | - | 5.5 | 1 | Practiced with draw.io.
Harini R | AB | AB | AB | AB | AB | AB
Kishore | Entity Framework-Code first approach | Changed grid to box method in profile creation details and user under me tab included in prototype - 2hrs Meeting with rafi - 1.5hr Discussion with Team about entity and relationship model- 2hrs | - | 5.5 | 1 | Gained knowledge in working with Balsamiq
Nagaraj | Entity and Relationship Model | Modification of Relationships among Entities- 1hr Meeting with rafi - 1.5 hr Discussion with team about entity and relationship model - 2hr | - | 4 | 3 | -
Ramakrishna | Entity and Relationship Model | Worked on datamodel-2hrs Project Review with Rafi - 1.5hr Discussed entities and relationship with team members - 1hrs | - | 4.5 | 2 | -
Sekhar | AB | AB | AB | AB | AB | AB
Yoga Dharshini G | Entity and Relationship Model | Modified User stories, acceptance criteria, assumptions and contraints- 2hrs Discussed entities and relationship with team members - 1hrs Project Review with Rafi - 1.5hr MOM updated and discussed - 1hr | - | 5.5hrs | 1 | -

## 18-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Brindha | Entity and Relationship Model | Discussion with Team about entity -2 hours Completed Entity model - Relationship and Operations - 3 hours Meeting with rafi - 30mins | - | 5:30 | 2 | Practiced with draw.io.
Chitrarasu | - | Completed prototype for Profile Management - 2 hours Discussion with team about data model - 1 hours Meeting with rafi - 30mins Completed entity relationship model(logical) - 3 hours | - | 6:30 | 2 | -
Dinesh Kumar | AB | AB | AB | AB | AB | AB
Gugan | Exploration on html layouts,Angular Concepts,HLD | Discussion with team about data model - 1 hr Worked on HLD in database dictionary - 2 hrs Exploration on html layouts and Angular Concepts - 3 hrs | - | 3 | 3 | -
Harini R | - | Completed prototype for Profile Management - 2 hours Discussion with team about data model - 1 hours Completed entity relationship model(logical) - 3 hours | - | 6 | 2 | -
Kishore | Entity,HLD | Finalized prototype - 2hrs Meeting with rafi - 30mins Discussion with Team about entity and relationship model- 2hrs | - | 4.5 | 2 | -
Nagaraj |  | Discussion with team about entity and Relationship - 1hr, Meeting with rafi - 30mins, Completed entity relationship model -2 hrs. | - | 3.5 | 3 | -
Ramakrishna | HLD | AB | AB | AB | AB | AB
Sekhar | AB | AB | AB | AB | AB | AB
Yoga Dharshini G | Entity,HLD,User story,Acceptance Criteria | Modified user story and finalized prototype- 2hrs Discussed entities and relationship with team members - 2hrs Project Review with Rafi - 30mins MOM updated and discussed - 1hr | - | 5:30hrs | 2

## 19-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Brindha | HLD and Angular | Discussion with team members about HLD and HTML layouts - 4 hours Created Database dictionary in HLD - 1 hour | - | 5 | 2 | -
Chitrarasu | HLD and Angular concepts | Completed Entity relationship model- 1 hours Discussed with team about HLD and HTML layouts - 4 hours | - | 5 | 2 | -
Dinesh Kumar | AB | AB | AB | AB | AB | AB
Gugan | HLD and Angular concepts Exploration on web api,HTML layouts | Discussed with team about HLD and HTML layouts - 4 hrs Worked on Entity Relationship model- 1 hr | - | 5 | 1.5 | -
Harini R | HLD and Angular concepts | Completed Entity relationship model- 1 hours Discussed with team about HLD and HTML layouts - 4 hours | - | 5 | 2 | -
Kishore | HLD,Layout | Finalized user story, acceptance criteria- 2hrs Discussed relationships and operations with team members - 2hrs | - | 4 | 2 | -
Nagaraj | Angular and HLD | Discussed with team about HLD -2 hours, Discussed with teamHTML layouts - 2 hours | - | 4 | 3 | -
Ramakrishna | HLD,Layout | AB | AB | AB | AB | AB
Sekhar | AB | AB | AB | AB | AB | AB
Yoga Dharshini G | HLD,Layout | Finalized user story, acceptance criteria- 2hrs Discussed relationships and operations with team members - 2hrs Created database dictionary and database model-1hr | - | 5hrs | 2 | -

## 20-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Brindha | HLD , Angular | Database dictionary in HLD - 2 hours Discussion with Team members about HLD and HTML layouts-2 hours | - | 4 | 2 | -
Chitrarasu | HTML layouts designing , HLD and Angular concepts | Worked on Database diagram and database dictionary in HLD - 2hours Discussion with team about HLD and HTML layouts - 2 hours Review with Anitha - 1 hour | - | 5 | 2 | -
Dinesh Kumar | AB | AB | AB | AB | AB | AB
Gugan | HLD ,Typescript overview,Exploration on Web api,Angular concepts | Discussion with team about HLD and HTML layouts - 2 hours Worked on HLD - 1.5 hr Review with Anitha - 1 hr | - | 3.5 | 2 | Practiced with database dictionary
Harini R | HTML layouts designing , HLD and Angular concepts | Worked on Database diagram and database dictionary in HLD - 2hours Discussion with team about HLD and HTML layouts - 2 hours Review with Anitha - 1 hour | - | 4 | 2 | -
Kishore | Entity Framework | Worked on layout(dashboard), HLD modules - 3hours Discussion with team about HLD and HTML layouts - 2 hours | - | 5 | 3 | Gained knowledge in working with Balsamiq
Nagaraj | HLD and Angular components | Discussion with team about HLD and HTML layouts - 2 hours, Worked on layout - 1 hour | - | 3 | 3 | -
Ramakrishna | Typescript | AB | AB | AB | AB | AB
Sekhar | AB | AB | AB | AB | AB | AB
Yoga Dharshini G | HLD, Layout | Discussed layout for homepage and dashboard,HLD-2hrs Worked on database dictionary and database diagram-2hrs | - | 4hrs | 3 | -

## 21-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Brindha | HLD , Web Api | Discussion with Team members and spilting the works - 1 hour worked on services- 2 hours Dicussion with Rafi(services,system architecture,DB diagram)-40 mins Meeting with Rafi(Customer meeting)-40 mins Soft skill session- 1 hour | - | 4:20 | 2 | -
Chitrarasu | Html layout for navigation. | Explored on Bootstrap( About navigation) - 1.5 hours Discussion with team about HLD and splitting of works - 1 hour Meeting with Rafi(Customer meeting) -40 mins Discussion with Rafi (discussed about services,HLD,DB diagram,audit fields) - 40 mins Soft skills session with TN team - 1 hour | - | 4hr 50mins | 2 | -
Gugan | DB diagram, HLD ,Typescript overview,Exploration on Web api,Angular concepts | Working on DB Diagram for ProjectDetails,Achievements,organisation and all history tables - 2 hrs Meeting with rafi(Customer Meeting) - 40 mins Discussion with team and Splitting of works - 1 hr Soft skills with TN team - 1 hr Discussion with Rafi(General Meet about Services,HTML layouts,DB Diagram) - 40 mins | - | 4.5 | 2.5 | -
Harini R | Web api sample version for User register | Worked on System architecture for profile management - 1 hour Discussion with team about HLD and splitting of works - 1 hour Discussion with Rafi (discussed about services,HLD,DB diagram,audit fields) - 40 mins Meeting with Rafi(Customer meeting) -40 mins Soft skills session with TN team - 1 hour | - | 4 hours 20 minutes | 2 | -
Kishore | HTML layout for home page | Explored on Bootstrap(Cards) - 1.5 hours Soft skills session with TN team - 1 hr Project review Meeting with Rafi - 40 mins Session with rafi - 40 mins Discussion with team HLD, Layout, Work split- 1 hour | - | 4 .5 | 2 | -
Nagaraj | Db Diagram,Exploration on Web API | Database diagram for -2 hours Meeting with Rafi(Customer)- 40 mins Session with Rafi about DB DIagram,services - 40 mins Soft Skill Session with TN Team - 1 hour Discussion with team about HLD and splitting of works - 1 hour | - | 4 | 1 | -
Ramakrishna | Services,Web API,TypeScript | Explored on TypeScript(TypeScript introduction,Datatypes,Implicit and Explicit)-2hrs Session with Rafi(Discussed about services,Interacions,Database diagram using sql server and HLD)-40mins Softskill session-1hr Meeting With Rafi-40mins Discussion with team about HLD and splitting of works - 1 hour Worked on Non-Functional Requirements and Services-2hrs | - | 4 | 3 | -3
Sekhar | HTML layouts designing for login page Exploring on Bootstrap | - | - | 2 | 1 | -
Yoga Dharshini G | HLD, System architecture | Discussion about HLD, system architechture, HTML layout and splitting of works - 1 hour Session with Rafi (week plan) - 40 mins Review with Rafi(discussed User story, datamodel)-40 mins Soft skills session with TN team - 1 hour Designed system architechture - 3 hours | - | 5:30 | 3 | -