## HTML_Estimation
S.No | Task | Sub Tasks | Estimation in Hrs
1 | Login | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 1
|  | HTML Validations | 2
|  | Web API Integration | 2
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 1
14
2 | Change password | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 1
|  | HTML Validations | 2
|  | Web API Integration | 2
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 1
14
Code Merging
Integration Testing
Compatibility testing
Deployment Documentation
3 | Forgot Password | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 1
|  | HTML Validations | 1
|  | Web API Integration | 1.5
|  | Web API - Service Implementation | 1.5
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 1
12
4 | Home Page | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 2
|  | HTML Validations | 1.5
|  | Web API Integration | 2
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 2
16.5
Code Merging
Integration Testing
Compatibility testing
Deployment Documentation
5 | Results Viewing Page(Cards) | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API Integration | 2
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 1
15
6 | Profile Viewing Page | Low Level Design - Sequence Diagram | 3
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API Integration | 1
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 1
15
Code Merging
Integration Testing
Compatibility testing
Deployment Documentation
7 | Create Profile | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 1
|  | HTML Validations | 1
|  | Web API Integration | 1
|  | Web API - Service Implementation | 1
|  | Swagger - API Documentation | 0.5
|  | Service Validations , Exception and Logging | 1
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 1
8.5
8 | Personal Details Entering Page | Low Level Design - Sequence Diagram | 4
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API Integration | 2
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 2
|  | Unit Testing | 2
19
Code Merging
Integration Testing
Compatibility testing
Deployment Documentation
9 | Education Details Page | Low Level Design - Sequence Diagram | 3
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API Integration | 2
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 2
17
10 | Project Details Page | Low Level Design - Sequence Diagram | 4
|  | HTML preparation | 3
|  | HTML Validations | 2
|  | Web API Integration | 1
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 2
15
11 | Skills Details Page | Low Level Design - Sequence Diagram | 4
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API Integration | 2
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 2
18
12 | Achievements | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 3
|  | HTML Validations | 1.5
|  | Web API Integration | 2
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 2
17.5
Integration Testing
Compatibility testing
Deployment Documentation
13 | User Creation | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 2
|  | HTML Validations | 1.5
|  | Web API Integration | 2
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 2
16.5
14 | Profile History | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 2
|  | HTML Validations | 1.5
|  | Web API Integration | 2
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 2
16.5
Code Merging
Integration Testing
Compatibility testing
Deployment Documentation