## HTML_Estimation
S.No | Task | Sub Tasks | Estimation in Hrs
1 | Login | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API Integration | 2
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1.5
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1.5
|  | Code Review | 2
|  | Unit Testing | 2
18
2 | Change password | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 2
|  | HTML Validations | 2
|  | Web API Integration | 2
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1.5
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1.5
|  | Code Review | 2
|  | Unit Testing | 2
19
3 | Forgot Password | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 1.5
|  | HTML Validations | 1
|  | Web API Integration | 2
|  | Web API - Service Implementation | 3
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 2
|  | Unit Testing | 1.5
17
|  | Code Merging | 9
|  | Integration Testing | 7
|  | Compatibility testing | 5
|  | Deployment Documentation | 6
27
4 | Home Page(Searcher,Creator,HR, Admin) | Low Level Design - Sequence Diagram | 4
|  | HTML preparation (Filters,User Dashboard,Search) | 4
|  | Web API Integration | 3
|  | Web API - Service Implementation | 4
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 4
|  | Code Cleanup | 2
|  | Code Review | 2
|  | Unit Testing | 2.5
27.5
5 | Results Viewing Page(After applying filters) | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 4
|  | Web API Integration | 2
|  | Web API - Service Implementation | 4
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 4
|  | Code Cleanup | 2
|  | Code Review | 2
|  | Unit Testing | 3
25
6 | Searched Profile Viewing Page | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 2
|  | Web API Integration | 3
|  | Web API - Service Implementation | 3
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 3
|  | Code Cleanup | 1
|  | Code Review | 2
|  | Unit Testing | 1
18
|  | Code Merging | 9
|  | Integration Testing | 7
|  | Compatibility testing | 5
|  | Deployment Documentation | 6
27
7 | Create Profile Page | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 1
|  | Web API Integration | 1
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 1
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 0.5
9.5
8 | Personal Details Page | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 4
|  | HTML Validations | 4
|  | Web API Integration | 2
|  | Web API - Service Implementation | 3
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 4
|  | Code Cleanup | 1
|  | Code Review | 2
|  | Unit Testing | 2
26
9 | Education Details Page | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 5
|  | HTML Validations | 2
|  | Web API Integration | 2
|  | Web API - Service Implementation | 3
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 3
|  | Code Cleanup | 1
|  | Code Review | 2
|  | Unit Testing | 1
23
10 | Project Details Page | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 3
|  | HTML Validations | 3
|  | Web API Integration | 2
|  | Web API - Service Implementation | 4
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 4
|  | Code Cleanup | 1
|  | Code Review | 2
|  | Unit Testing | 2
23
11 | Skills Details Page | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API Integration | 2
|  | Web API - Service Implementation | 3
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 2
|  | Unit Testing | 2
19
12 | Achievements | Low Level Design - Sequence Diagram | 4
|  | HTML preparation | 3
|  | HTML Validations | 2
|  | Web API Integration | 3
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 3
|  | Code Cleanup | 2
|  | Code Review | 2
|  | Unit Testing | 2
25
|  | Code Merging | 5
|  | Integration Testing | 4
|  | Compatibility testing | 4
|  | Deployment Documentation | 4
17
13 | User Creation | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 2
|  | HTML Validations | 2
|  | Web API Integration | 2
|  | Web API - Service Implementation | 3
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 2
|  | Unit Testing | 2
19
14 | Edit User Details | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API Integration | 2
|  | Web API - Service Implementation | 3
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 2
|  | Unit Testing | 1
17
|  | Code Merging | 4
|  | Integration Testing | 4
|  | Compatibility testing | 5
|  | Deployment Documentation | 4
17
14 | Profile History | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 2
|  | Web API Integration | 3
|  | Web API - Service Implementation | 3
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 3
|  | Code Cleanup | 1
|  | Code Review | 2
|  | Unit Testing | 1
19
15 | Profile History View | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 3
|  | Web API Integration | 2
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 1
|  | Code Cleanup | 1
|  | Code Review | 2
|  | Unit Testing | 1
15
|  | Code Merging | 4
|  | Integration Testing | 4
|  | Compatibility testing | 5
|  | Deployment Documentation | 4
17
|  | Total hours | 425