## 05-04-2022
Resource Name | Action Point / Impediments | Status | Comments
Harini R & Chitrarasu | finding solution for github account problem
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Harini R | Requirement refining and storing of lower hierarchy designated people | Work flow completed | How a user can view his lower hierarchy person on the system | 5 | 2
Chitrarasu V | Working to store the profile in database | User Story completed | How to show the lower profile in dashboard | 5 | 2
Sekhar | Requirement refining | User Workflow | How can store lower hierarchy on the system. | 5 | 2
Nagaraj K | Hierarchy Mapping | Workflow based on Filters | how to map the lower profiles under higher profiles | 5 | 2
Kishore kumar A N | Requirement refining | User Workflow | How to show the lower profile in dashboard | 5 | 2
Ramakrishna | Requirements and hierachy storage | User Flow for creation | How to add restrictions | 5 | 2
Brindha M | Hierarchy Mapping | User Flow for searcher | how to map hierarchy | 5 | 2
Gugan RB | Working to store the profile in database | User Story completed,User Flow for searcher | How to show the lower profile in dashboard | 5 | 2
Yoga Dharshini | What are to be maintained as master data and role mapping | Overall flow for both user | Hierarchy mapping | 5 | 2
Dinesh Kumar

## 06-04-2022
Resource Name | Action Point / Impediments | Status | Comments
Harini R & Chitrarasu | finding solution for github account problem | Completed | Signed in another user
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Brindha | Acceptance criteria for Admin | Discussion and meeting with rafi - 1hour Team Discussion- 2hours Made minor changes in user story - 1 hour Acceptance criteria for Creator and Searcher - Completed - 2hours | Acceptance criteria for Admin | 6 | 1 | Having doubt in Share feature for acceptance criteria
Chitrarasu | Exploration on Web API Assumptions | Meeting with rafi - 1 hrs Made minor changes in user story as discussed in previous meeting - 1.5 hrs Discussion with Gugan about Assumptions - 1 hrs Discussion with Gugan about Constraints - 1.5 hrs Discussion with team on admin's user story,work flow,prototype and hierarchial mapping - 2 hrs | Assumptions | 7 | 1 | Having clarity in different assumptions was difficult
Dinesh Kumar | AB | AB | AB | AB | AB | AB
Gugan | Exploration on Entity Framework Assumptions | Meeting with rafi - 1 hrs Made minor changes in user story as discussed in previous meeting - 1.5 hrs Discussion with Chitrarasu about Assumptions - 1 hrs Discussion with Chitrarasu about Constraints - 1.5 hrs Discussion with team on admin's user story,work flow,prototype and hierarchial mapping - 2 hrs | Assumptions | 7 | 1 | Having clarity in different assumptions was difficult
Harini | Creation of prototype for entering project details in the system,View page | Requirement refining - Project Details - 1hour Prototype for Register, Entering personal details pages - 1.5 hours Made minor changes in user story as discussed in previous meeting - 1.5 hours Discussion with team and Meeting with rafi - 3hours | Share feature in protoype - holded | 7 | 1 | Having doubt in creation for prototype of share feature
Kishore | Creation of prototype for Viewing their profiles | Requirement Refining- Break information for experience -1hr Prototypes for Login,Dashboard,Objective and Skills-2hrs Meeting with Rafi-1hr Meeting with Team Regarding Work assigning-2hrs | Profile Tempalte View | 6 | 1 | not having any idea how Profile template looks like
Nagaraj | Acceptance criteria for Admin | Acceptance criteria for Creator and Searcher - 2 hours Team Discussion on MoM scoped requirements-2 hours Meeting with raffi - 1 hour Hierarchy mapping - 30 minutes | - | 5.5 | 1 | -
Ramakrishna | Creation of prototype for Viewing their profiles | Requirement Refining- Profile details-1hr,Prototypes for Register,Education,Objective and Skills-2hrs,Meeting with Rafi-1hr,Meeting with Team Regarding Work assigning and Changes-2hrs | Profile Template while downloading and view | 6 | 1 | not having any idea how Profile template looks like
Sekhar | Exploring on Entity Framework. | Discussion and meeting with rafi - 1 hrs. Minor changes in user story and workflow - 1:30 hrs. Added admin as an another user, created admin workflow - 1 hrs. Discussion with team members - 2 hrs. | profile searcher can review another user profile. | 5:30 hrs | 1:30 hrs | Whether profile searcher or admin can review others profile.
Yoga Dharshini G | Admin controls and user profile reviews | Added admin as another user,created admin user story - 1:30hrs Made minor changes in user story and work flow - 2hr Discussion with Rafi - 1:30hrs Discussion with team members and Sekhar - 1:30 hr | Admin's other controls and Profile searcher or admin should review profiles or not | 6:30 Hrs | 3 hrs | Stuck with admin's other control flow and validation or verification has to be done or not

## 07-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Brindha | Exploration on Web API | Prototype for home page - 2 hours Acceptance criteria for Admin and HR - 1 hour Meeting with Raffi - 1.5 hour Team discussion - 2 hours | - | 6.5 | 1 | Practice with Balsamiq.
Chitrarasu | Exploration on WPI | Create prototype for view the created Profile - 2hrs Meeting with rafi - 1.5hr Discussion with Team about Prototype and admin user story - 3hrs | - | 6.5 | 1 | Practice with Balsamiq.
Dinesh Kumar | AB | AB | AB | AB | AB | AB
Gugan | Exploration on Entity Framework | Meeting with Rafi - 1.5 hrs Discussion with team about Prototype and admin user story - 3 hrs Prototype for HR user creation - 30 mins Prototype for Profile searcher view - 1.5hr | sharing profile,status | 6.5 | 1 | Doubt in share feature and status feature
Harini R | Exploration on web api | Created prototype for create profile page and home page - 2.5hrs Meeting with rafi - 1.5hr Discussion with Team about Prototype and admin user story - 3hrs | - | 7 | 1 | Doubt in share feature
Kishore | Entity Framework-Code first approach | Prototypes for Change Password and My profile-2hrs Meeting with Rafi-1hr Meeting with Team Regarding Work assigning-2hrs |  | 5 | 2
Nagaraj | - | Prototype for Login page - 30 mins Acceptance criteria for Admin and HR - 1 hour Meeting with Raffi - 1.5 hour Team discussion - 2.5 hours | - | 5.5 | 2 | Practiced with Balsamiq.
Ramakrishna | Entity Framework-Code first approach | Created prototypes for profile searcher view and HR user creation-2hrs,Meeting with Rafi-1.5hrs,Meeting with team regarding work assingnig and prototype designing-3hrs | sharing profile | 6.5 | 1 | Doubt in share feature and status feature
Sekhar | Exploration on Web API | Meeting with rafi - 1hr. Discussion with team member about prototype designing - 3hrs. Made changes in userstory (Creater,Searcher) & Created Admin, HR Partner userstory - 2hrs. | - | 6 | 1:30 | -
Yoga Dharshini G | Exploring prototype and Entityframework | Made changes in workflow (Creater,Searcher) & Created Admin, HR Partner workflow - 3hrs Discussion with team members - 2hrs Review with Rafi - 1:30hrs MOM updated and discussed - 1hr | Mail System | 7:30 | 2 | No clarification in mail system and share feature

## 08-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Brindha | Entity and Relationship Model | Prototype for create profile - 2 hours Meeting with raffi - 1 hour Discussion with team members- 3 hours | - | 6 | 1 | Practiced with Balsamiq.
Chitrarasu | Entity and Relationship Model | Changed prototype for view page of created Profile - 2hrs Meeting with rafi - 1hr Discussion with Team about prototype and entity and relationship model- 3hrs | - | 6 | 1 | Gained knowledge in working with Balsamiq
Dinesh Kumar | AB | AB | AB | AB | AB | AB
Gugan | Exploration on Entity Framework,Entity and Relationship model | Create prototype for view the created Profile - 2hrs Meeting with rafi - 1hr Discussion with Team about modify the prototype - 2hrs Discussion with team about entity and relationship model - 1hr | - | 6 | 1 | Practiced with Balsamiq,Have to work in entity model
Harini R | Entity and relationship model | Changed prototype for create profile page - 2hrs Meeting with rafi - 1hr Discussion with Team about Prototype and entity and relationship model - 3hrs | - | 6 | 1 | Gained knowledge in working with Balsamiq
Kishore | Entity Framework-Code first approach | Prototypes for View my profile for searcher-2hrs Meeting with Rafi-1hr Meeting with Team Regarding Work assigning-2hrs |  | 5 | 2 | -
Nagaraj | Entity and Relationship | Modified the user stories - 1.5 hours Meeting with raffi - 1 hour Discussion with team about changing prototype's profile details -2 hours | - | 4.5 | 3 | Practiced with Balsamiq.
Ramakrishna | Entity Relationship | Prototype for Login and Password changes- 2 hours Meeting with raffi - 1 hour Discussion with team members regarding prototypes - 3 hours |  | 6 | 2 | Practiced with Balsamiq.
Sekhar | Entity Relationship | Meeting with raffi - 1 hour Discussion with team members regarding prototypes - 3 hours Prototype for profile creator - 1 hour | - | 5 | 1 | Practiced with Balsamiq.
Yoga Dharshini G | Exploring prototype and Entityframework | Added Prototype for Searcher, Admin and Reporting person Homepage - 2hrs Discussion with team members - 2hrs Review with Rafi - 1hr MOM updated and discussed - 1hr | - | 6hrs | 1 | -

## 09-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Brindha | Entity and Relationship Model | Created Entity model - master data,User details,Relationship- 2 hours Meeting with raffi - 1.5 hour Discussion with Team about modify the prototype - 2 hours Discussion with team about entity and relationship model - 3 hours | - | 6.5 | 1 | Practiced with draw.io.
Chitrarasu | Entity and Relationship Model | Changed prototype for view page of created Profile - 2hrs Meeting with rafi - 1hr Discussion with Team about prototype and entity and relationship model- 3hrs | - | 6 | 1 | Gained knowledge in working with Balsamiq
Dinesh Kumar | AB | AB | AB | AB | AB | AB
Gugan | Exploration on Entity Framework,Entity and Relationship model | Created entity model - master data,User details,Relationship- 2hrs Meeting with rafi - 1.5 hr Discussion with Team about modify the prototype - 2hrs Discussion with team about entity and relationship model - 1hr | - | 6.5 | 1 | Practiced with draw.io.
Harini R | Entity and relationship model | Changed prototype for create profile page - 2hrs Meeting with rafi - 1hr Discussion with Team about Prototype and entity and relationship model - 3hrs | - | 6 | 1 | Gained knowledge in working with Balsamiq
Kishore | Entity Framework-Code first approach | Prototypes for View my profile for searcher-2hrs Meeting with Rafi-1hr Meeting with Team Regarding Work assigning-2hrs |  | 5 | 2 | -
Nagaraj | AB | AB | AB | AB | AB | AB
Ramakrishna | Entity Framework | Protypes for Login page maintained same font sizes-2hrs,meeting with Rafi-1hr,Meeting with Team Regarding Work spilting-2hrs | - | 6 | 1
Sekhar | Entity Framework | Protypes for user creation and change font size-1hrs. meeting with Rafi-1hr. Meeting with Team Regarding Work spilting-2hrs | - | 4 | 2 | Practiced with Balsamiq.
Yoga Dharshini G | Exploring prototype and Entityframework | Added Prototype for Searcher, Admin and Reporting person Homepage - 2hrs Discussion with team members - 2hrs Review with Rafi - 1hr MOM updated and discussed - 1hr | - | 6hrs | 1 | -

## 11-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Brindha | Entity and Relationship Model | Created Entity model - master data,User details,Relationship- 2 hours Meeting with raffi - 1.5 hour Discussion with Team about modify the prototype - 2 hours Discussion with team about entity and relationship model - 3 hours | - | 6.5 | 1 | Practiced with draw.io.
Chitrarasu | Entity and Relationship Model | Changed prototype for view page of created Profile,Admin & HR home page - 2hrs Meeting with rafi - 1.5hr Discussion with Team about prototype and entity and relationship model- 3hrs | - | 6.5 | 1 | Gained knowledge in working with Balsamiq
Dinesh Kumar | AB | AB | AB | AB | AB | AB
Gugan | Exploration on Entity Framework,Entity and Relationship model | Created entity model - master data,User details,Relationship- 2hrs Meeting with rafi - 1.5 hr Discussion with Team about modify the prototype - 2hrs Discussion with team about entity and relationship model - 1hr | - | 6.5 | 1 | Practiced with draw.io.
Harini R | Entity and relationship model | Changed prototype for create profile page - 2hrs Meeting with rafi - 1hr Discussion with Team about Prototype and entity and relationship model - 3hrs | - | 6 | 1 | Gained knowledge in working with Balsamiq
Kishore | Entity Framework-Code first approach | Prototype for Profile history and Profile view- 2hrs. Meeting with rafi - 1.5 hr Discussion with Team about modify the prototype - 2hrs Discussion with Team about prototype and entity and relationship model- 1hrs | - | 6.5 | 1 | Gained knowledge in working with Balsamiq
Nagaraj | AB | AB | AB | AB | AB | AB
Ramakrishna | Entity Framework-Code first approach | AB | - | - | - | -
Sekhar | AB | AB | AB | AB | AB | AB
Yoga Dharshini G | Exploring prototype and Entity | Modified Prototype Homepage- 2hrs Discussion with team members - 2hrs Project Review with Rafi - 1hr MOM updated and discussed - 1hr | - | 6hrs | 1 | -

## 12-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Brindha | Entity and Relationship Model | Modified Entity model - master data,User details,Relationship,Data entries in excel - 2 hours Meeting with raffi - 1.5 hour Discussion with Team about entity and prototype-3 hours | - | 6.5 | 1 | Practiced with draw.io.
Chitrarasu | Entity and Relationship Model | Changed prototype for view page of created Profile,Admin & HR home page - 2hrs Meeting with rafi - 1.5hr Discussion with Team about entity and relationship model- 2hrs | - | 5.5 | 1 | Gained knowledge in working with Balsamiq
Dinesh Kumar | AB | AB | AB | AB | AB | AB
Gugan | Exploration on Entity Framework,Entity and Relationship model | Created entity model - master data,User details,Relationship- 2hrs Meeting with rafi - 1.5 hr Discussion with team about entity and relationship model - 2hr | - | 5.5 | 1 | Practiced with draw.io.
Harini R | Entity and relationship model | Changed prototype for create profile page and home page - 2hrs Meeting with rafi - 1.5hr Discussion with Team about entity and relationship model - 2hrs | - | 5.5 | 1 | Gained knowledge in working with Balsamiq
Kishore | Entity Framework-Code first approach | Changed Prototype for Searcher Home Page- 1hrs. Created the prototype for Total Number of User and Approved user-2hrs Meeting with rafi - 1.5hr Discussion with Team about modify entity and relationship model- 2hrs | - | 6.5 | 1 | Gained knowledge in working with Balsamiq
Nagaraj | Entity and Relationship Model | Created entity model - master data,User details,Relationship- 2hrs Meeting with rafi - 1.5 hr Discussion with team about entity and relationship model - 2hr | - | 2 | 2 | -
Ramakrishna | Entity and Relationship Model | Modified Entity model - master data,User details,Relationship,Data entries in excel - 2 hours Meeting with raffi - 1.5 hour Discussion with Team about entity and prototype-3 hours | - | 6.5 | 1 | Practiced with draw.io.
Sekhar | Entity Framework-Code first approach | Meeting with rafi - 1.5 hr, Discussion with Team about prototype and entity and relationship model- 2 hrs, Creating for entity tables in draw.io - 2hrs, Modified for user creation in prototype - 1hr | - | 6.5 | 1 | Practiced with draw.io.
Yoga Dharshini G | Exploring prototype and Entity | Modified Prototype of Homepage- 1hrs Discussed entities and relationship with team members - 2hrs Project Review with Rafi - 1.5hr MOM updated and discussed - 1hr | - | 5.5hrs | 1 | -

## 13-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Brindha | Entity and Relationship Model | Modified Entity model - Relationship - 2 hours Meeting with raffi - 1.5 hour Discussion with Team about entity and prototype-2 hours | - | 5.5 | 1 | Practiced with draw.io.
Chitrarasu | Entity and Relationship Model | Changed grid to box method in profile creation details and user under me tab included in prototype - 2hrs Meeting with rafi - 1.5hr Discussion with Team about entity and relationship model- 2hrs | - | 5.5 | 1 | Gained knowledge in working with Balsamiq
Dinesh Kumar | AB | AB | AB | AB | AB | AB
Gugan | Entity and Relationship Model | Modified Entity model - Relationship - 2 hours Meeting with raffi - 1.5 hour Discussion with Team about entity and prototype-2 hours | - | 5.5 | 1 | Practiced with draw.io.
Harini R | AB | AB | AB | AB | AB | AB
Kishore | Entity Framework-Code first approach | Changed grid to box method in profile creation details and user under me tab included in prototype - 2hrs Meeting with rafi - 1.5hr Discussion with Team about entity and relationship model- 2hrs | - | 5.5 | 1 | Gained knowledge in working with Balsamiq
Nagaraj | Entity and Relationship Model | Modification of Relationships among Entities- 1hr Meeting with rafi - 1.5 hr Discussion with team about entity and relationship model - 2hr | - | 4 | 3 | -
Ramakrishna | Entity and Relationship Model | Worked on datamodel-2hrs Project Review with Rafi - 1.5hr Discussed entities and relationship with team members - 1hrs | - | 4.5 | 2 | -
Sekhar | AB | AB | AB | AB | AB | AB
Yoga Dharshini G | Entity and Relationship Model | Modified User stories, acceptance criteria, assumptions and contraints- 2hrs Discussed entities and relationship with team members - 1hrs Project Review with Rafi - 1.5hr MOM updated and discussed - 1hr | - | 5.5hrs | 1 | -

## 18-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Brindha | Entity and Relationship Model | Discussion with Team about entity -2 hours Completed Entity model - Relationship and Operations - 3 hours Meeting with rafi - 30mins | - | 5:30 | 2 | Practiced with draw.io.
Chitrarasu | - | Completed prototype for Profile Management - 2 hours Discussion with team about data model - 1 hours Meeting with rafi - 30mins Completed entity relationship model(logical) - 3 hours | - | 6:30 | 2 | -
Dinesh Kumar | AB | AB | AB | AB | AB | AB
Gugan | Exploration on html layouts,Angular Concepts,HLD | Discussion with team about data model - 1 hr Worked on HLD in database dictionary - 2 hrs Exploration on html layouts and Angular Concepts - 3 hrs | - | 3 | 3 | -
Harini R | - | Completed prototype for Profile Management - 2 hours Discussion with team about data model - 1 hours Completed entity relationship model(logical) - 3 hours | - | 6 | 2 | -
Kishore | Entity,HLD | Finalized prototype - 2hrs Meeting with rafi - 30mins Discussion with Team about entity and relationship model- 2hrs | - | 4.5 | 2 | -
Nagaraj |  | Discussion with team about entity and Relationship - 1hr, Meeting with rafi - 30mins, Completed entity relationship model -2 hrs. | - | 3.5 | 3 | -
Ramakrishna | HLD | AB | AB | AB | AB | AB
Sekhar | AB | AB | AB | AB | AB | AB
Yoga Dharshini G | Entity,HLD,User story,Acceptance Criteria | Modified user story and finalized prototype- 2hrs Discussed entities and relationship with team members - 2hrs Project Review with Rafi - 30mins MOM updated and discussed - 1hr | - | 5:30hrs | 2

## 19-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Brindha | HLD and Angular | Discussion with team members about HLD and HTML layouts - 4 hours Created Database dictionary in HLD - 1 hour | - | 5 | 2 | -
Chitrarasu | HLD and Angular concepts | Completed Entity relationship model- 1 hours Discussed with team about HLD and HTML layouts - 4 hours | - | 5 | 2 | -
Dinesh Kumar | AB | AB | AB | AB | AB | AB
Gugan | HLD and Angular concepts Exploration on web api,HTML layouts | Discussed with team about HLD and HTML layouts - 4 hrs Worked on Entity Relationship model- 1 hr | - | 5 | 1.5 | -
Harini R | HLD and Angular concepts | Completed Entity relationship model- 1 hours Discussed with team about HLD and HTML layouts - 4 hours | - | 5 | 2 | -
Kishore | HLD,Layout | Finalized user story, acceptance criteria- 2hrs Discussed relationships and operations with team members - 2hrs | - | 4 | 2 | -
Nagaraj | Angular and HLD | Discussed with team about HLD -2 hours, Discussed with teamHTML layouts - 2 hours | - | 4 | 3 | -
Ramakrishna | HLD,Layout | AB | AB | AB | AB | AB
Sekhar | AB | AB | AB | AB | AB | AB
Yoga Dharshini G | HLD,Layout | Finalized user story, acceptance criteria- 2hrs Discussed relationships and operations with team members - 2hrs Created database dictionary and database model-1hr | - | 5hrs | 2 | -

## 20-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Brindha | HLD , Angular | Database dictionary in HLD - 2 hours Discussion with Team members about HLD and HTML layouts-2 hours | - | 4 | 2 | -
Chitrarasu | HTML layouts designing , HLD and Angular concepts | Worked on Database diagram and database dictionary in HLD - 2hours Discussion with team about HLD and HTML layouts - 2 hours Review with Anitha - 1 hour | - | 5 | 2 | -
Dinesh Kumar | AB | AB | AB | AB | AB | AB
Gugan | HLD ,Typescript overview,Exploration on Web api,Angular concepts | Discussion with team about HLD and HTML layouts - 2 hours Worked on HLD - 1.5 hr Review with Anitha - 1 hr | - | 3.5 | 2 | Practiced with database dictionary
Harini R | HTML layouts designing , HLD and Angular concepts | Worked on Database diagram and database dictionary in HLD - 2hours Discussion with team about HLD and HTML layouts - 2 hours Review with Anitha - 1 hour | - | 4 | 2 | -
Kishore | Entity Framework | Worked on layout(dashboard), HLD modules - 3hours Discussion with team about HLD and HTML layouts - 2 hours | - | 5 | 3 | Gained knowledge in working with Balsamiq
Nagaraj | HLD and Angular components | Discussion with team about HLD and HTML layouts - 2 hours, Worked on layout - 1 hour | - | 3 | 3 | -
Ramakrishna | Typescript | AB | AB | AB | AB | AB
Sekhar | AB | AB | AB | AB | AB | AB
Yoga Dharshini G | HLD, Layout | Discussed layout for homepage and dashboard,HLD-2hrs Worked on database dictionary and database diagram-2hrs | - | 4hrs | 3 | -

## 21-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Brindha | HLD , Web Api | Discussion with Team members and spilting the works - 1 hour worked on services- 2 hours Dicussion with Rafi(services,system architecture,DB diagram)-40 mins Meeting with Rafi(Customer meeting)-40 mins Soft skill session- 1 hour | - | 4:20 | 2 | -
Chitrarasu | Html layout for navigation. | Explored on Bootstrap( About navigation) - 1.5 hours Discussion with team about HLD and splitting of works - 1 hour Meeting with Rafi(Customer meeting) -40 mins Discussion with Rafi (discussed about services,HLD,DB diagram,audit fields) - 40 mins Soft skills session with TN team - 1 hour | - | 4hr 50mins | 2 | -
Gugan | DB diagram, HLD ,Typescript overview,Exploration on Web api,Angular concepts | Working on DB Diagram for ProjectDetails,Achievements,organisation and all history tables - 2 hrs Meeting with rafi(Customer Meeting) - 40 mins Discussion with team and Splitting of works - 1 hr Soft skills with TN team - 1 hr Discussion with Rafi(General Meet about Services,HTML layouts,DB Diagram) - 40 mins | - | 4.5 | 2.5 | -
Harini R | Web api sample version for User register | Worked on System architecture for profile management - 1 hour Discussion with team about HLD and splitting of works - 1 hour Discussion with Rafi (discussed about services,HLD,DB diagram,audit fields) - 40 mins Meeting with Rafi(Customer meeting) -40 mins Soft skills session with TN team - 1 hour | - | 4 hours 20 minutes | 2 | -
Kishore | HTML layout for home page | Explored on Bootstrap(Cards) - 1.5 hours Soft skills session with TN team - 1 hr Project review Meeting with Rafi - 40 mins Session with rafi - 40 mins Discussion with team HLD, Layout, Work split- 1 hour | - | 4 .5 | 2 | -
Nagaraj | Db Diagram,Exploration on Web API | Database diagram for -2 hours Meeting with Rafi(Customer)- 40 mins Session with Rafi about DB DIagram,services - 40 mins Soft Skill Session with TN Team - 1 hour Discussion with team about HLD and splitting of works - 1 hour | - | 4 | 1 | -
Ramakrishna | Services,Web API,TypeScript | Explored on TypeScript(TypeScript introduction,Datatypes,Implicit and Explicit)-2hrs Session with Rafi(Discussed about services,Interacions,Database diagram using sql server and HLD)-40mins Softskill session-1hr Meeting With Rafi-40mins Discussion with team about HLD and splitting of works - 1 hour Worked on Non-Functional Requirements and Services-2hrs | - | 4 | 3 | -3
Sekhar | HTML layouts designing for login page Exploring on Bootstrap | - | - | 2 | 1 | -
Yoga Dharshini G | HLD, System architecture | Discussion about HLD, system architechture, HTML layout and splitting of works - 1 hour Session with Rafi (week plan) - 40 mins Review with Rafi(discussed User story, datamodel)-40 mins Soft skills session with TN team - 1 hour Designed system architechture - 3 hours | - | 5:30 | 3 | -

## 22-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Brindha | HLD , Web Api | Modified on Services-2 hours Interactions(Services and Actions)-1 hour Discussion with team members - 1 hour Meeting with rafi- 1 hour Timesheet and SVN session with TN team - 30 mins | - | 5:30 | 2 | -
Chitrarasu | Web API | Worked on Sidebar Navigation bar - 2hours Timesheet and SVN session with TN team - 30 minutes Project review Meeting with Rafi - 1 hr Discussed system architechture, HTML layout, DB diagrams, Services and Interactions with team - 1 hr | - | 4hours 30minutess | 2 hours | -
Gugan | DB diagram, HLD ,Typescript overview,Exploration on Web api,Angular concepts | Working on DB Diagram for ProjectDetails,Achievements,organisation and all history tables & its relation - 2 hrs Meeting with rafi(Customer Meeting) - 1 hr Timesheet and SVN session with TN team - 30 mins Discussed system architechture, HTML layout, DB diagrams, Services and Interactions with team - 1 hour Understanding of System Architecture & HTML layout - 30 mins | - | 5 | 2 | -
Harini R | Web api sample version for User register | Worked on System architecture for profile management - 2 hours Discussed system architechture, HTML layout, DB diagrams, Services and Interactions with team - 1 hour Meeting with Rafi(Customer meeting) - 1hour Timesheet and SVN session with TN team - 30 mins | - | 4.5 | 2 | -
Kishore | HTML layout for home page | Worked on Cards in Layout - 1.5 hours Timesheet and SVN session with TN team - 30 mins Project review Meeting with Rafi - 1 hr Discussed system architechture, HTML layout, DB diagrams, Services and Interactions with team - 1 hour | - | 4 .5 | 2 | -
Nagaraj | - | Database diagram for -2 hours Meeting with Rafi(Customer)- 1 hour Timesheet and SVN session with TN team - 30 mins Discussion WIth Team members- 1 hour | - | 4.5 | 2 | -
Ramakrishna | Services,Web API | Explored on TypeScript(Implicit and Explicit,enums,functions tried sample programs using functions)-2hrs Meeting With Rafi-1hr Timesheet and SVN session-30mins Discussion with team Members - 1hour Worked on Services-2hrs | - | 4 | 3 | -
Sekhar | Exploring on Bootstrap | Timesheet and SVN session with TN team - 30 mins Project review Meeting with Rafi - 1 hr Discussed system architechture, HTML layout, DB diagrams, Services and Interactions with team - 1 hr HTML layout for login page - 1 hr 30 mins Entity model with opearation - 1hr | - | 5 | 2 | -
Yoga Dharshini G | Web API, System Architechture | Discussed system architechture, HTML layout, DB diagrams, Services and Interactions with team - 1 hour Review with Rafi(discussed HTML layout, system architechture, Services, datamodel) - 1 hour Timesheet and SVN session with TN team - 30 mins Designed system architechture - 3:30 mins | - | 6 hrs | 2 | -

## 23-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Brindha | HLD , Web Api | Discussion with team members (Services and DB diagrams) - 1 hour Meeting with rafi(Reviewed Services,System architecture,HTML layout)- 1 hour Softskill with TN Team- 1:30 hours Modified Services - 2 hours | - | 5:30 | 2 | -
Chitrarasu | Web API,working on profile template | Discussed DB diagrams, Services with team - 1 hour Softskill with TN Team - 1:30 hours Review with Rafi(discussed HTML layout, system architechture, Services) - 1 hour Modified Common page layout - 30 minutes | - | 4hours 30minutess | 2 hours | -
Gugan | DB diagram, HLD ,Typescript overview,Exploration on Web api,Angular concepts | Discussion with team members (Services and DB diagrams) - 1 hour Meeting with rafi(Customer Meeting) - 1 hr Softskill with TN Team- 1:30 hours Worked on Services(including methods and naming) - 1 hr Worked on DB diagrams - 30 mins | - | 4 | 1 | -
Harini R | Web api sample version for User register | Modified the System architecture for profile management - 30 minutes Discussed DB diagrams, Services and Interactions with team - 1 hour Meeting with Rafi(Reviewed Services,HTML layout,system architecture) - 1hour Softskill with TN Team- 1 hour 30minutes | - | 4 | 2 | -
Kishore | HTML layout for home page | Created the prototype for Change password and modified the layout for cards - 1 hrs Discussed DB diagrams, Services with team - 1 hrs Review with Rafi(discussed HTML layout, system architechture, Services) - 1 hour Softskill with TN Team - 1:30 hrs | - | 4 .5 | 1 | -
Nagaraj | search Operation under Profile services | Meeting with Rafi(Customer)- 1 hour softskill session with TN team- 1.5 hours Discussion WIth Team members about services - 1 hour Modification on services- 1 hour | - | 4 | 1 | -
Ramakrishna | Services,Web API | Activity with TN team- 1.5 hours Discussion WIth Team members about services - 1 hour Meeting with Rafi- 1 hour Moified services,created WebAPI - 2hour | - | 5:30 | 2 | -
Sekhar | Exploring on Bootstrap | ab | - | - | - | -
Yoga Dharshini G | Web API | Discussed DB diagrams, Services with team - 1 hrs Review with Rafi(discussed HTML layout, system architechture, Services) - 1 hour Softskill with TN Team - 1:30 hrs Modified system architechture,working on web API - 2 hrs | - | 5:30 hrs | 2 | -

## 25-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Brindha | Web Api | Discussion with Team members(Services and operations)-1 hour Meeting with Rafi(Services,Interactions)-1 hour Modified Services and Datamodel - 2 hours | - | 4 hours | 2 | -
Chitrarasu | Working on Wizard menu for getting Profile Details,Web API | Home Page Layout completed - 3hours Discussion with team about Services and Operations - 1 hour Meeting with Rafi(Reviewed Services,Operations,Interactions) - 1hour | - | 5hours | 2 hours | -
Gugan | Exploration on Angular Concepts Exploration on Web API Exploration on EF-Code First | Discussion with team about Services and Operations - 1 hr Working on Web Api - 2 hrs | - | 3 | 3 | -
Harini R | Web api sample version for User register | Discussion with team about Services and Operations - 1 hour Meeting with Rafi(Reviewed Services,Operations,Interactions) - 1hour Working on Web api - 2hours | - | 4 | 2 | -
Kishore | Working on Layout for forgot password password | Cards Layout completed - 3hours Discussion with team about Services and Operations - 1 hour Meeting with Rafi(Reviewed Services,Operations,Interactions) - 1hour | - | 4 | 1 | -
Nagaraj | MyProfile HTML Layout | Meeting with Rafi(customer) reviewed operations on Profile service - 1 hour, Discussion WIth Team members about services and Operations - 1 hour, Created MyProfile page with Accordian - 2 hours | - | 4 | 2 | -
Ramakrishna | Services,Web API | ab | - | - | - | -
Sekhar | Exploring on Bootstrap | ab | - | - | - | -
Yoga Dharshini G | Web API | Discussed Operations with team - 1 hr Review with Rafi(discussed Services and Interactions) - 1 hr Modified services and Interactions, working on web API - 2 hrs | - | 4 hrs | 2 | -

## 26-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Brindha | Exploring on Web Api | Discussion with Team members(Web Api and layout)-2 hour Meeting with Rafi(Services)-1 hour Modified Services and working on web api(dbcontext) - 2 hours | - | 5 hours | 2 | -
Chitrarasu | Working on Wizard menu for getting Profile Details,Web API | Discussion with team about HTML layouts - 1 hour Meeting with Rafi(Reviewed Services and operations) - 1 hour Did HTML Estimation for home page and forgot password page- 30minutes Working on HTML layouts(wizard menu) - 3hours | - | 5hours 30 minutes | 2 hours | -
Gugan | Exploration on Angular Concepts Exploration on Web API Exploration on EF-Code First | Discussion with team on Web API - 2 hr Meeting with Rafi(Customer Meeting) - 1 hr HTML Layout for User Creation Page - 1.5 hr Created estimation for Education,project,skills page - 30 min | - | 5 | 3 | -
Harini R | Web api sample version for User register | Discussion with team about web api - 2 hours Meeting with Rafi(Reviewed Services and operations) - 1hour Did HTML Estimation for results viewing page(cards),Profile viewing page and personal details entering page - 30 minutes Modified services and operations- 30minutes Working on web api for user creation(dbContext,migrations) - 2 hours | - | 4 | 2 | -
Kishore | Working on Layout | Forgot Password Layout completed - 2hours Created estimation for Login and change password-30min Meeting with Rafi(customer meeting) - 1hour discussion with team about html-1hours | - | 4.5 | 2 | -
Nagaraj | MyProfile HTML Layout | Meeting with Rafi(customer) reviewed operations on Profile service - 1 hour, Discussion WIth Team members about services and Operations - 1 hour, modification of MyProfile page and create profile page with Accordian - 2 hours | - | 4 | 2 | -
Ramakrishna | Web API | Created Webapi Get and Post end points for user-2hrs Discussion with team about web api and HTML layouts - 2 hours Meeting with Rafi(services,Estimation,HTML Layouts)-1hour | - | 5 | 3 | -
Sekhar | Exploring on Bootstrap | ab | - | - | - | -
Yoga Dharshini G | Web API, HTML Layout | Discussed Web API with team - 2 hr Review with Rafi(discussed Services) - 1 hr Decided estimation for profile history,user creation,achievements and working on layout- 2 hrs | - | 4 hrs | 2 | -

## 27-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Brindha | Exploring on Web Api | (9:30am - 10:30am)- Softskills session with TN team - 1 hour (11:00am - 12:30 pm)- Modified Services and Operations - 1 hour 30 minutes (1:00pm - 1:22pm)- Meeting with Rafi(Estimation,Services)-22 mins (2:30pm - 4:00pm) - Worked on Web Api(DbContext and migrations)-1 hour 30 minutes (4:30pm - 5:30pm) - HTML Reviewed and Discussed - 1 hour (9:00pm - 10:00pm)- Modified changes in Login page - 1 hour | - | 6 hours 22 minutes | 1 | -
Chitrarasu | Working on Wizard menu for getting Profile Details,Web API | (8:45am - 9.30am) - Working on HTML Layout - 45minutes (9:30 am - 10:30am) - Softskills session with TN team - 1hour (10:30 am - 10:50am) - Tea Break - 20minutes (11:00am - 12.30pm) - Reviewed Services and operations - 1hour 30minutes (12:30pm - 1:00pm) - Lunch time - 30minutes (1:00pm - 1:22pm) - Meeting with Rafi[reviewed HTML estimation] - 22minutes (2:30pm - 4:00pm) - Published HTML code in github and modified the changes in HTML layout - 1hour 30minutes (4.30pm - 5:30pm) - Modified the changes in Home page - 1hour (5.30pm - 6:00pm) - Discussion with team about splitting of works for HTML layout - 30minutes (9:00pm - 10:00pm) - Working on wizard method HTML Layout- 1hour | - | 6hours 30 minutes | 2 hours | -
Gugan | Exploration on Angular Concepts Exploration on Web API Exploration on EF-Code First | Working on HTML Layout(User Creation) : 8.45 - 9:30 (45 mins) Softskill session(Problem Solving) : 9:30 - 10:20 (50 mins) Tea break : 10:20 - 10:40 (20 mins) Updated Timesheet : 10:40 - 10:55 (15 mins) Discussed on Services and Operations : 11.00 - 12.30 (90 mins) Idle : 12:30 - 12:55 (25 mins) Meeting with Rafi(Customer Meeting) : 1:00 - 1:20 (20 mins) Lunch Break : 1.20 - 2.00 (40 mins) Idle : 2:00 - 2:30 (30 mins) Splitting of works & consolidating all opearions in HTML Layouts : 2:30 - 4:00 (90 mins) Exploration on WebApi : 4:00 - 4:30 (30 mins) Coffee break : 4:30 - 4:45 (15 mins) Exploration on web api : 4:45 - 5:45 (60 mins) Brushing up of Basics(C#,ADO.Net) : 7:00 - 8:00 (60 mins) Learning on Web Api,EF : 9:00 - 10:00 (60 mins) | - | 4 hours and 50 minutes | 5 hours and 20 minutes | -
Harini R | WEebapi | (8:45am - 9.30am) - Did estimation for HTML pages - 45minutes (9:30 am - 10:30am) - Softskills session with TN team - 1hour (11:15am - 12.30pm) - Reviewed Services and operations - 1hour 15minutes (1:00pm - 1:22pm) - Meeting with Rafi[reviewed HTML estimation] - 22minutes (2:30pm - 4:00pm) - Published HTML code in github and modified the changes in HTML layout - 1hour 30minutes (4.30pm - 5:30pm) - Modified the changes in Login page - 1hour (5.30pm - 6:00pm) - Discussion with team about splitting of works for HTML layout - 30minutes (9:00pm - 10:00pm) - Modified the changes in Login page - 1hour | - | 6 hours 22 minutes | 1 | -
Kishore | Working on Layout | Working on HTML Layout(Change Password) : 8.45am - 9:30am (45 mins) Softskill session(Problem Solving) : 9:30am - 10:20am (50 mins) Tea break : 10:20am - 10:45am (20 mins) Modified HTML(Forgot Password): 10:45am-11:00am (15 mins) Revised the concept of mvc,sql,ado.net and c# : 11:00am - 12:00am (1 hour) discussed about services and operation: 12:00pm-1:00pm (1 hour) Meeting with Rafi(Customer Meeting) : 1:00pm - 1:20pm (20 mins) Lunch Break : 1.20 - 2.10 (50 mins) Splitting of works & consolidating all opearions in HTML Layouts : 2:30 - 4:00 (90 mins) Coffee break : 4:30 - 4:45 (15 mins) modified the html layout for change password and forgot password :4:45pm - 5:30pm(45 mins) Review meeting with anitha : 5:40pm - 6:00pm(20 mins) Created the layout for Profile Histroy : 9:30pm - 10:30pm(1 hour) | - | 5 hours 35minutes | 3 hours 35 minutes | -
Nagaraj | MyProfile HTML Layout | (8.45 am- 9-15 am) - Modification on myprofile page -30mins (9.30 am - 10.30 am) - Softskills session with TN team - 1 hour (11am - 12.30 am)- creation of create page - 1.30hour (1pm-1.20pm) Meeting with Rafi(Estimation,Services)-22 mins (2:30pm - 4:00pm) - Splitting of works,changes & consolidating all opearions in HTML Layouts - 1.5 hours (4:30pm - 5:30pm) - Review changes in MyProfile page and CreateProfile page - 1hour (9pm-10.30pm) - applied collapsible on wizard page - 1.5 hours | - | 6 hours 22 minutes | 1 | -
Ramakrishna | Web API | Created Webapi Get and Post end points for user-2hrs Discussion with team about web api and HTML layouts - 2 hours Meeting with Rafi(services,Estimation,HTML Layouts)-1hour | - | 5 | 3 | -
Sekhar | Exploring on Bootstrap | ab | - | - | - | -
Yoga Dharshini G | HTML Layout, Angular | Updated and pushed User story, MOM and Timesheet - 30 mins (08:30 am - 09:00 am) Decided HTML estimation - 30 mins (09:00 am - 09:30 am) Softskill session with TN Team - 1 hr (09:30 am - 10:30 am) Modified HTML and discussed services with team - 2 hrs (11:00 am - 01:00 pm) Review with Rafi(discussed Services) - 22 mins (01:00 pm- 01:22 pm) HTML Reviewed and discussed - 3:30 hrs (2:30pm - 06:00pm) Modified estimation for profile history,user creation,achievements - 30 mins (07:30pm - 08:00pm) Modified Wizard layout - 1:30 hrs (08:30 pm - 10:00 pm) Explored Angular - 40 mins (10:00 pm - 10:40 pm) | - | 07:52 hrs(at office) 02:40 hrs | 2 | -

## 28-04-2022
Resource | Task Name | Task Type | Start Time | End Time | Total Time
Brindha | Discussed Estimation | Project | 9:00 | 9:30 | 0:30 | Split | Time
| Reviewed HTML layout | Project | 10:00 | 12:00 | 2:00 | Project | 5:00
| Customer Meeting | Project | 13:00 | 13:45 | 0:45 | Non Project | 0:00
| Team meeting | Project | 14:30 | 15:15 | 0:45 | Exploration | 1:30
| Lunch | Lunch and Break | 13:45 | 14:10 | 0:25 | Meeting | 0:00
| Morning Break | Lunch and Break | 11:20 | 11:30 | 0:10 | Customer Review | 0:00
| Evening Break | Lunch and Break | 15:45 | 16:00 | 0:15 | Lunch and Break | 0:50
| Exploration on Typescript topics | Exploration | 15:30 | 17:00 | 1:30 | TOTAL | 7:20
| Modified HTML layouts<Educational details> | Project | 20:30 | 21:30 | 1:00
0:00
0:00
0:00
0:00
0:00
0:00
Chitrarasu | Reviewed estimation sheet | Project | 9:00 | 9:30 | 0:30 | Split | Time
| Worked on HTML Layout for Wizard page | Project | 9:30 | 10:30 | 1:00 | Project | 6:30
| Morning Break | Lunch and Break | 10:30 | 11:00 | 0:30 | Non Project | 0:00
| Reviewed HTML layout(Login,Forgot Password,Chnage Password,User Creation) | Project | 11:00 | 12:30 | 1:30 | Exploration | 1:30
| Customer Meeting | Project | 13:00 | 13:45 | 0:45 | Meeting | 0:00
| Lunch Break | Lunch and Break | 13:45 | 14:15 | 0:30 | Customer Review | 0:00
| Team meeting | Project | 14:30 | 15:15 | 0:45 | Lunch and Break | 1:00
| Typescript topic | Exploration | 15:30 | 17:00 | 1:30 | TOTAL | 9:00
| Working on HTML layout for wizard Layout | Project | 20:00 | 22:00 | 2:00
0:00
0:00
0:00
0:00
0:00
0:00
Gugan | Discussed Estimation | Project | 9:00 | 9:45 | 0:45 | Split | Time
| Worked on HTML layout for User Creation Page | Project | 9:45 | 10:30 | 0:45 | Project | 5:30
| Morning Break | Lunch and Break | 10:30 | 11:00 | 0:30 | Non Project | 0:45
| Worked on HTML layout for User Creation Page | Project | 11:00 | 13:00 | 2:00 | Exploration | 1:30
| Customer Meeting | Project | 13:00 | 13:45 | 0:45 | Meeting | 0:00
| Lunch Break | Lunch and Break | 13:45 | 14:15 | 0:30 | Customer Review | 0:00
| Team Meeting | Non Project | 14:30 | 15:15 | 0:45 | Lunch and Break | 1:20
| Learned Angular <Topics> | Exploration | 15:30 | 17:00 | 1:30 | TOTAL | 9:05
| Evening Break | Lunch and Break | 17:10 | 17:30 | 0:20
| Worked on HTML Layout for Wizard(skill)page | Project | 17:30 | 18:45 | 1:15
0:00
| HTML layout wizard(In progress) |  |  |  | 0:00
0:00
0:00
0:00
Harini | Reviewed estimation sheet | Project | 9:00 | 9:30 | 0:30 | Split | Time
| Worked on HTML layout for login page | Project | 9:35 | 10:30 | 0:55 | Project | 6:45
| Morning break | Lunch and Break | 10:30 | 11:00 | 0:30 | Non Project | 0:00
| Reviewed the HTML layout | Project | 11:10 | 13:00 | 1:50 | Exploration | 1:30
| Customer meeting | Project | 13:00 | 13:45 | 0:45 | Meeting | 0:00
| Lunch break | Lunch and Break | 13:45 | 14:15 | 0:30 | Customer Review | 0:00
| Team meeting | Project | 14:30 | 15:15 | 0:45 | Lunch and Break | 1:00
| Exploration on typescript topics | Exploration | 15:30 | 17:00 | 1:30 | TOTAL | 9:15
| Modified changes in Login page(HTML) | Project | 17:00 | 17:30 | 0:30
| Worked on HTML layout for home page | Project | 21:00 | 22:30 | 1:30
0:00
0:00
0:00
0:00
0:00
Kishore | worked on HTML layout for Change Password | Project | 9:00 | 9:50 | 0:50 | Split | Time
| worked on HTML layout for Forgot Password | Project | 10:10 | 11:00 | 0:50 | Project | 5:40
| Morning Break | Lunch and Break | 11:00 | 11:20 | 0:20 | Non Project | 0:50
| Reviewed the HTML layout | Project | 11:30 | 12:30 | 1:00 | Exploration | 0:00
| Customer Meeting | Project | 13:00 | 13:45 | 0:45 | Meeting | 0:00
| Lunch Break | Lunch and Break | 13:45 | 14:15 | 0:30 | Customer Review | 0:00
| Team meeting | Non Project | 14:30 | 15:20 | 0:50 | Lunch and Break | 0:50
| Angular session | Project | 15:30 | 17:00 | 1:30 | TOTAL | 7:20
| Working on HTML layout for Change Password | Project | 18:00 | 18:45 | 0:45
0:00
0:00
0:00
0:00
0:00
0:00
Nagaraj | Team Meeting | Project | 10:00 | 10:10 | 0:10 | Split | Time
| Soft Skill | Non Project | 10:15 | 11:00 | 0:45 | Project | 5:30
| Customer Meeting | Project | 11:00 | 11:20 | 0:20 | Non Project | 1:45
| Soft Skill | Non Project | 11:30 | 12:30 | 1:00 | Exploration | 0:00
| Lunch | Lunch and Break | 12:30 | 13:00 | 0:30 | Meeting | 0:00
| Morning Break | Lunch and Break | 11:20 | 11:30 | 0:10 | Customer Review | 0:00
| Evening Break | Lunch and Break | 15:45 | 16:00 | 0:15 | Lunch and Break | 0:55
| Learned Angular <Topics> | Project | 16:00 | 18:00 | 2:00 | TOTAL | 8:10
| Working on HTML layout | Project | 18:00 | 21:00 | 3:00
0:00
0:00
0:00
0:00
0:00
0:00
Ramakrishna | Team Meeting | Project | 8:45 | 9:00 | 0:15 | Split | Time
| Worked on Web api(SOC,Factory pattern) | Project | 9:00 | 11:00 | 2:00 | Project | 5:00
| Morning Break | Lunch and Break | 11:10 | 11:30 | 0:20 | Non Project | 0:30
| Worked on Web api | Project | 11:30 | 13:00 | 1:30 | Exploration | 2:55
| Customer Meeting | Project | 13:00 | 13:45 | 0:45 | Meeting | 0:00
| Lunch Break | Lunch and Break | 13:45 | 14:15 | 0:30 | Customer Review | 0:00
| Logging | Exploration | 14:20 | 15:00 | 0:40 | Lunch and Break | 1:10
| Tried Console logging | Non Project | 15:00 | 15:30 | 0:30 | TOTAL | 9:35
| TypeScript Session | Exploration | 15:30 | 17:00 | 1:30
| Evening Break | Lunch and Break | 17:00 | 17:20 | 0:20
| Logging | Project | 17:20 | 17:50 | 0:30
| TypeScript and Entity Framework | Exploration | 19:15 | 20:00 | 0:45
0:00
0:00
0:00
Sekhar | Team Meeting | Project | 0:00 | 0:00 | 0:00 | Split | Time
| Soft Skill | Non Project | 0:00 | 0:00 | 0:00 | Project | 0:00
| Customer Meeting | Project | 0:00 | 0:00 | 0:00 | Non Project | 0:00
| Soft Skill | Non Project | 0:00 | 0:00 | 0:00 | Exploration | 0:00
| Lunch | Lunch and Break | 0:00 | 0:00 | 0:00 | Meeting | 0:00
| Morning Break | Lunch and Break | 0:00 | 0:00 | 0:00 | Customer Review | 0:00
| Evening Break | Lunch and Break | 0:00 | 0:00 | 0:00 | Lunch and Break | 0:00
| Learned Angular <Topics> | Project | 0:00 | 0:00 | 0:00 | TOTAL | 0:00
| Working on HTML layout | Project | 0:00 | 0:00 | 0:00
0:00
0:00
0:00
0:00
0:00
0:00
Yoga dharshini | Modified estimation sheet and updated MOM | Project | 9:00 | 10:00 | 1:00 | Split | Time
| Modified HTML layout | Project | 10:00 | 10:30 | 0:30 | Project | 6:45
| Morning break | Lunch and Break | 10:30 | 11:00 | 0:30 | Non Project | 1:15
| Modified HTML layout and GIT push | Project | 11:00 | 13:00 | 2:00 | Exploration | 0:00
| Customer meeting | Project | 13:00 | 13:45 | 0:45 | Meeting | 0:00
| Lunch break | Lunch and Break | 13:45 | 14:30 | 0:45 | Customer Review | 0:00
| Modified estimation sheet | Project | 15:30 | 16:00 | 0:30 | Lunch and Break | 1:30
| Angular session | Non Project | 15:30 | 16:00 | 0:30 | TOTAL | 9:30
| Evening Break | Lunch and Break | 16:00 | 16:15 | 0:15
| Angular session | Non Project | 16:15 | 17:00 | 0:45
| Team discussion on HTML layout | Project | 17:00 | 18:00 | 1:00
| Worked on wizard layout | Project | 21:30 | 22:30 | 1:00
0:00
0:00
0:00

## 29-04-2022
Resource | Task Name | Task Type | Start Time | End Time | Total Time
Brindha | Updated Timesheet and Reviewed HTML layouts | Project | 8:30 | 9:30 | 1:00 | Split | Time | Project
| Soft Skill | Non Project | 9:30 | 10:30 | 1:00 | Project | 6:35 | Non Project
| Morning Break | Lunch and Break | 10:30 | 10:45 | 0:15 | Non Project | 1:00 | Exploration
| Modified Education details page(HTML) | Project | 10:45 | 12:45 | 2:00 | Exploration | 0:45 | Meeting
| Customer Meeting | Customer Review | 12:50 | 13:20 | 0:30 | Meeting | 0:45 | Customer Review
| Lunch | Lunch and Break | 13:20 | 13:40 | 0:20 | Customer Review | 0:30 | Lunch and Break
| Worked on Web api(Dbcontext and Services) | Project | 13:40 | 16:15 | 2:35 | Lunch and Break | 0:50
| Evening Break | Lunch and Break | 16:15 | 16:30 | 0:15 | TOTAL | 10:25
| Explored on Web api(Controllers) | Exploration | 16:30 | 17:15 | 0:45
| Team Meeting(Webapi and html layouts) | Meeting | 17:15 | 18:00 | 0:45
| Modified Personal details page(HTML) | Project | 20:30 | 21:30 | 1:00
0:00
0:00
0:00
0:00
Chitrarasu | Worked on HTML for Wizard method | Project | 8:30 | 9:30 | 1:00 | Split | Time
| Soft Skill | Non Project | 9:30 | 10:30 | 1:00 | Project | 7:15
| Morning Break | Lunch and Break | 10:30 | 10:45 | 0:15 | Non Project | 1:00
| Reviewed estimation sheet | Project | 10:45 | 12:45 | 2:00 | Exploration | 0:00
| Customer meeting | Customer Review | 12:50 | 13:30 | 0:40 | Meeting | 0:45
| Lunch | Lunch and Break | 13:30 | 14:00 | 0:30 | Customer Review | 0:40
| Worked on responsive sidebar | Project | 14:10 | 16:00 | 1:50 | Lunch and Break | 1:15
| Evening Break | Lunch and Break | 16:00 | 16:30 | 0:30 | TOTAL | 10:55
| Worked on the modifications in wizard method | Project | 16:30 | 17:10 | 0:40
| Team Meeting | Meeting | 17:15 | 18:00 | 0:45
| Worked on the modifications in wizard method | Project | 21:00 | 22:45 | 1:45
0:00
0:00
0:00
Gugan | Worked on HTML layout Page(project) | Project | 8:30 | 9:30 | 1:00 | Split | Time
| Soft Skill | Non Project | 9:30 | 10:30 | 1:00 | Project | 6:45
| Morning Break | Lunch and Break | 10:30 | 10:40 | 0:10 | Non Project | 1:00
| Modifications on HTML layout Page(project) | Project | 10:40 | 12:40 | 2:00 | Exploration | 1:30
| Customer meeting | Customer Review | 12:50 | 13:30 | 0:40 | Meeting | 0:45
| Lunch | Lunch and Break | 13:30 | 14:10 | 0:40 | Customer Review | 0:40
| Discussed on Web Api(Services & Models) | Project | 14:20 | 16:00 | 1:40 | Lunch and Break | 1:10
| Evening Break | Lunch and Break | 16:00 | 16:20 | 0:20 | TOTAL | 11:50
| Discussed on HTML layout(Modifications) | Project | 16:20 | 17:10 | 0:50
| Team Meeting | Meeting | 17:15 | 18:00 | 0:45
| Exploration on Web api & angular topics | Exploration | 18:30 | 20:00 | 1:30
| Working on Web api models | Project | 20:30 | 21:45 | 1:15
0:00
0:00
0:00
Harini | Worked on HTML for Home page | Project | 8:30 | 9:30 | 1:00 | Split | Time
| Soft Skill | Non Project | 9:30 | 10:30 | 1:00 | Project | 7:10
| Morning Break | Lunch and Break | 10:30 | 10:45 | 0:15 | Non Project | 1:00
| Reviewed estimation sheet and modified home page | Project | 10:45 | 12:45 | 2:00 | Exploration | 0:00
| Customer meeting | Customer Review | 12:50 | 13:30 | 0:40 | Meeting | 0:45
| Lunch | Lunch and Break | 13:30 | 14:00 | 0:30 | Customer Review | 0:40
| Worked on responsive sidebar | Project | 14:10 | 16:00 | 1:50 | Lunch and Break | 1:15
| Evening Break | Lunch and Break | 16:00 | 16:30 | 0:30 | TOTAL | 10:50
| Worked on the modififications in home page | Project | 16:30 | 17:10 | 0:40
| Team Meeting | Meeting | 17:15 | 18:00 | 0:45
| Worked on home page and integrating it with responsive sidebar | Project | 21:20 | 23:00 | 1:40
0:00
0:00
0:00
Kishore | Worked on HTML page(Change Password) | Project | 9:00 | 9:25 | 0:25 | Split | Time
| Soft Skill | Non Project | 9:30 | 10:30 | 1:00 | Project | 6:20
| Morning Break | Non Project | 10:30 | 10:55 | 0:25 | Non Project | 1:25
| Worked on HTML page(Change Password) | Project | 11:30 | 12:50 | 1:20 | Exploration | 0:00
| Customer meeting | Project | 12:50 | 13:30 | 0:40 | Meeting | 0:45
| Lunch | Lunch and Break | 13:30 | 14:10 | 0:40 | Customer Review | 0:00
| Worked on Modified Education Page | Project | 14:15 | 16:00 | 1:45 | Lunch and Break | 1:10
| Break | Lunch and Break | 16:00 | 16:30 | 0:30 | TOTAL | 9:40
| Worked on HTML layout(Education) | Project | 16:00 | 17:10 | 1:10
| Team Meeting | Meeting | 17:15 | 18:00 | 0:45
| Worked on HTML layout(Achivements) | Project | 21:00 | 22:00 | 1:00
0:00
0:00
0:00
0:00
Nagaraj | Modifying MyProfile page | Project | 8:45 | 9:30 | 0:45 | Split | Time
| Soft Skill | Non Project | 9:30 | 10:30 | 1:00 | Project | 6:20
| Morning Break | Lunch and Break | 10:30 | 11:00 | 0:30 | Non Project | 2:20
| Modifying MyProfile page | Project | 11:00 | 12:00 | 1:00 | Exploration | 0:00
| Timesheet Entering | Non Project | 12:00 | 12:30 | 0:30 | Meeting | 0:45
| Customer meeting | Project | 12:30 | 13:20 | 0:50 | Customer Review | 0:00
| Modifying MyProfile page | Project | 14:00 | 15:00 | 1:00 | Lunch and Break | 1:00
| Modifying create Page | Project | 15:00 | 15:45 | 0:45 | TOTAL | 10:25
| Break | Lunch and Break | 16:00 | 16:30 | 0:30
| Modifying create Page | Project | 16:30 | 17:00 | 0:30
| Team Meeting | Meeting | 17:00 | 17:45 | 0:45
| Modifying MyProfile page | Project | 21:30 | 23:00 | 1:30
| Exploration on web API | Non Project | 23:00 | 23:50 | 0:50
0:00
0:00
Ramakrishna | Team Meeting | Project | 8:30 | 8:45 | 0:15 | Split | Time
| WebAPI | Project | 8:45 | 9:30 | 0:45 | Project | 6:30
| Soft Skill | Non Project | 9:30 | 10:30 | 1:00 | Non Project | 1:00
| WebAPI | Project | 10:40 | 12:40 | 2:00 | Exploration | 1:00
| Customer Meeting | Customer Review | 12:45 | 13:30 | 0:45 | Meeting | 0:00
| Lunch Break | Lunch and Break | 13:30 | 14:10 | 0:40 | Customer Review | 0:45
| Team meeting on WebAPI | Project | 14:10 | 15:00 | 0:50 | Lunch and Break | 1:00
| webAPI | Project | 15:00 | 16:00 | 1:00 | TOTAL | 10:15
| Evening Break | Lunch and Break | 16:00 | 16:20 | 0:20
| WebAPI | Project | 16:20 | 18:00 | 1:40
| Explored on Defensive Coding,Typescript | Exploration | 19:00 | 20:00 | 1:00
0:00
0:00
0:00
0:00
Sekhar | Team Meeting | Project | 0:00 | 0:00 | 0:00 | Split | Time
| Soft Skill | Non Project | 0:00 | 0:00 | 0:00 | Project | 0:00
| Customer Meeting | Project | 0:00 | 0:00 | 0:00 | Non Project | 0:00
| Soft Skill | Non Project | 0:00 | 0:00 | 0:00 | Exploration | 0:00
| Lunch | Lunch and Break | 0:00 | 0:00 | 0:00 | Meeting | 0:00
| Morning Break | Lunch and Break | 0:00 | 0:00 | 0:00 | Customer Review | 0:00
| Evening Break | Lunch and Break | 0:00 | 0:00 | 0:00 | Lunch and Break | 0:00
| Learned Angular <Topics> | Project | 0:00 | 0:00 | 0:00 | TOTAL | 0:00
| Working on HTML layout | Project | 0:00 | 0:00 | 0:00
0:00
0:00
0:00
0:00
0:00
0:00
Yoga dharshini | Refined Estimation and Worked on HTML | Project | 8:30 | 9:30 | 1:00 | Split | Time
| Softskill with TN Team | Non Project | 9:30 | 10:30 | 1:00 | Project | 6:50
| Morning Break | Lunch and Break | 10:30 | 11:00 | 0:30 | Non Project | 1:00
| Modified Wizard Layout | Project | 11:00 | 12:30 | 1:30 | Exploration | 0:00
| Updated Timesheet and MOM and pushed in GIT | Project | 12:30 | 13:50 | 1:20 | Meeting | 0:45
| Customer Review | Customer Review | 13:50 | 14:20 | 0:30 | Customer Review | 0:30
| Lunch Break | Lunch and Break | 14:20 | 14:45 | 0:25 | Lunch and Break | 1:25
| Refined Estimation | Project | 14:45 | 15:45 | 1:00 | TOTAL | 10:30
| Evening Break | Lunch and Break | 15:45 | 16:15 | 0:30
| Modified Wizard Layout | Project | 16:15 | 17:15 | 1:00
| Team dicussion on HTML layout and Work split | Meeting | 17:15 | 18:00 | 0:45
| Worked on modifications in Wizard method | Project | 21:00 | 22:00 | 1:00
0:00
0:00
0:00

## 30-04-2022
Resource | Task Name | Task Type | Start Time | End Time | Total Time
Brindha | Updated Timesheet and Reviewed HTML layouts | Project | 8:30 | 9:30 | 1:00 | Split | Time | Project
| Soft Skill | Non Project | 10:10 | 11:00 | 0:50 | Project | 6:35 | Non Project
| Morning Break | Lunch and Break | 11:00 | 11:15 | 0:15 | Non Project | 0:50 | Exploration
| Modified Personal details page(HTML) | Project | 10:45 | 12:45 | 2:00 | Exploration | 0:45 | Meeting
| Customer Meeting | Customer Review | 13:30 | 14:20 | 0:50 | Meeting | 0:45 | Customer Review
| Lunch | Lunch and Break | 13:20 | 13:40 | 0:20 | Customer Review | 0:50 | Lunch and Break
| Worked on Web api(Dbcontext and Services) | Project | 13:40 | 16:15 | 2:35 | Lunch and Break | 0:50
| Evening Break | Lunch and Break | 16:15 | 16:30 | 0:15 | TOTAL | 10:35
| Explored on Web api(Controllers) | Exploration | 16:30 | 17:15 | 0:45
| Team Meeting(Webapi and html layouts) | Meeting | 17:15 | 18:00 | 0:45
| Modified Personal details page(HTML) | Project | 20:30 | 21:30 | 1:00
0:00
0:00
0:00
0:00
Chitrarasu | Worked on HTML for Wizard method | Project | 8:30 | 9:30 | 1:00 | Split | Time
| Soft Skill | Non Project | 9:40 | 10:45 | 1:05 | Project | 7:05
| Morning Break | Lunch and Break | 10:50 | 11:00 | 0:10 | Non Project | 1:05
| Worked on HTML for Wizard method | Project | 11:05 | 12:45 | 1:40 | Exploration | 1:00
| Lunch | Lunch and Break | 12:50 | 13:30 | 0:40 | Meeting | 0:30
| Customer Meeting | Customer Review | 13:30 | 14:20 | 0:50 | Customer Review | 0:50
| Modified the changes in HTML | Project | 14:35 | 16:00 | 1:25 | Lunch and Break | 1:20
| Evening Break | Lunch and Break | 16:00 | 16:30 | 0:30 | TOTAL | 11:50
| Exploration on Angular topics | Exploration | 16:30 | 17:30 | 1:00
| Team Meeting | Meeting | 17:30 | 18:00 | 0:30
| Worked on HTML layout for Project details page | Project | 20:00 | 23:00 | 3:00
0:00
0:00
0:00
Gugan | Worked on Web Api(User service) | Project | 8:30 | 9:30 | 1:00 | Split | Time
| Soft Skill | Non Project | 9:40 | 10:45 | 1:05 | Project | 7:00
| Morning Break | Lunch and Break | 10:50 | 11:10 | 0:20 | Non Project | 1:05
| Worked on Web Api(User service) | Project | 11:10 | 13:00 | 1:50 | Exploration | 1:30
| Customer meeting | Customer Review | 13:30 | 14:20 | 0:50 | Meeting | 0:30
| Lunch | Lunch and Break | 13:00 | 13:30 | 0:30 | Customer Review | 0:50
| Discussed on Web Api(Services & Models) | Project | 14:20 | 16:00 | 1:40 | Lunch and Break | 1:00
| Evening Break | Lunch and Break | 16:00 | 16:10 | 0:10 | TOTAL | 11:55
| Discussed on HTML layout(Modifications) | Project | 16:10 | 17:10 | 1:00
| Team Meeting | Meeting | 17:30 | 18:00 | 0:30
| Exploration on Web api & angular topics | Exploration | 18:30 | 20:00 | 1:30
| Working on Web api models | Project | 20:30 | 22:00 | 1:30
0:00
0:00
0:00
Harini | Worked on HTML for Home page | Project | 8:30 | 9:30 | 1:00 | Split | Time
| Soft Skill | Non Project | 9:40 | 10:45 | 1:05 | Project | 6:50
| Morning Break | Lunch and Break | 10:50 | 11:10 | 0:20 | Non Project | 1:05
| Worked on HTML | Project | 10:25 | 13:00 | 2:35 | Exploration | 1:00
| Lunch | Lunch and Break | 12:50 | 13:30 | 0:40 | Meeting | 0:30
| Customer Meeting | Customer Review | 13:30 | 14:20 | 0:50 | Customer Review | 0:50
| Modified the changes in HTML | Project | 14:45 | 16:00 | 1:15 | Lunch and Break | 1:30
| Evening Break | Lunch and Break | 16:00 | 16:30 | 0:30 | TOTAL | 11:45
| Learned Angular topics | Exploration | 16:30 | 17:30 | 1:00
| Team Meeting | Meeting | 17:30 | 18:00 | 0:30
| Worked on HTML layout(Educational details page) | Project | 20:30 | 22:30 | 2:00
0:00
0:00
0:00
Kishore | Worked on HTML page(Forgot Password) | Project | 8:30 | 9:40 | 1:10 | Split | Time
| Soft Skill | Non Project | 9:40 | 10:50 | 1:10 | Project | 6:35
| Morning Break | Non Project | 10:50 | 11:20 | 0:30 | Non Project | 1:40
| Worked on HTML page(Change Password) | Project | 11:30 | 12:50 | 1:20 | Exploration | 1:45
| Customer meeting | Project | 12:50 | 13:30 | 0:40 | Meeting | 0:20
| Lunch | Lunch and Break | 13:30 | 14:10 | 0:40 | Customer Review | 0:00
| Learned Angular topics | Exploration | 14:15 | 16:00 | 1:45 | Lunch and Break | 1:10
| Break | Lunch and Break | 16:00 | 16:30 | 0:30 | TOTAL | 11:30
| Modified cards layout | Project | 16:00 | 17:40 | 1:40
| Team Meeting | Meeting | 17:40 | 18:00 | 0:20
| Modified the layout for Profile Histroy | Project | 21:00 | 22:45 | 1:45
0:00
0:00
0:00
0:00
Nagaraj | Modifying MyProfile page | Project | 9:00 | 10:00 | 1:00 | Split | Time
| Soft Skill | Non Project | 10:10 | 11:00 | 0:50 | Project | 5:45
| Morning Break | Lunch and Break | 11:00 | 11:30 | 0:30 | Non Project | 1:20
| Modifying create Page | Project | 11:30 | 12:00 | 0:30 | Exploration | 1:00
| Timesheet Entering | Non Project | 12:00 | 12:30 | 0:30 | Meeting | 0:15
| Modifying MyProfile page | Project | 14:00 | 15:00 | 1:00 | Customer Review | 0:00
| Modifying create Page | Project | 15:00 | 15:45 | 0:45 | Lunch and Break | 1:00
| Break | Lunch and Break | 16:00 | 16:30 | 0:30 | TOTAL | 9:20
| Modifying create Page | Project | 16:30 | 17:00 | 0:30
| Team Meeting | Meeting | 17:00 | 17:15 | 0:15
| Modifying MyProfile page | Project | 21:30 | 23:30 | 2:00
| Angular exploration | Exploration | 16:30 | 17:30 | 1:00
0:00
0:00
Ramakrishna | Team Meeting | Project | 8:30 | 8:45 | 0:15 | Split | Time
| WebAPI | Project | 8:45 | 9:30 | 0:45 | Project | 6:30
| Soft Skill | Non Project | 9:30 | 10:30 | 1:00 | Non Project | 1:00
| WebAPI | Project | 10:40 | 12:40 | 2:00 | Exploration | 1:00
| Customer Meeting | Customer Review | 12:45 | 13:30 | 0:45 | Meeting | 0:00
| Lunch Break | Lunch and Break | 13:30 | 14:10 | 0:40 | Customer Review | 0:45
| Team meeting on WebAPI | Project | 14:10 | 15:00 | 0:50 | Lunch and Break | 1:00
| webAPI | Project | 15:00 | 16:00 | 1:00 | TOTAL | 10:15
| Evening Break | Lunch and Break | 16:00 | 16:20 | 0:20
| WebAPI | Project | 16:20 | 18:00 | 1:40
| Explored on Defensive Coding,Typescript | Exploration | 19:00 | 20:00 | 1:00
0:00
0:00
0:00
0:00
Sekhar | Team Meeting | Project | 0:00 | 0:00 | 0:00 | Split | Time
| Soft Skill | Non Project | 0:00 | 0:00 | 0:00 | Project | 0:00
| Customer Meeting | Project | 0:00 | 0:00 | 0:00 | Non Project | 0:00
| Soft Skill | Non Project | 0:00 | 0:00 | 0:00 | Exploration | 0:00
| Lunch | Lunch and Break | 0:00 | 0:00 | 0:00 | Meeting | 0:00
| Morning Break | Lunch and Break | 0:00 | 0:00 | 0:00 | Customer Review | 0:00
| Evening Break | Lunch and Break | 0:00 | 0:00 | 0:00 | Lunch and Break | 0:00
| Learned Angular <Topics> | Project | 0:00 | 0:00 | 0:00 | TOTAL | 0:00
| Working on HTML layout | Project | 0:00 | 0:00 | 0:00
0:00
0:00
0:00
0:00
0:00
0:00
Yoga dharshini | Finalized Estimation and Worked on Wizard Layout | Project | 8:30 | 9:30 | 1:00 | Split | Time
| Softskill with TN Team | Non Project | 9:30 | 10:40 | 1:10 | Project | 6:15
| Morning Break | Lunch and Break | 10:40 | 11:00 | 0:20 | Non Project | 1:10
| Modified Wizard Layout | Project | 11:00 | 12:30 | 1:30 | Exploration | 1:30
| Updated Timesheet and MOM and pushed in GIT | Project | 12:30 | 13:50 | 1:20 | Meeting | 0:15
| Lunch Break | Lunch and Break | 12:50 | 13:25 | 0:35 | Customer Review | 0:50
| Customer Meeting | Customer Review | 13:30 | 14:20 | 0:50 | Lunch and Break | 1:10
| Refined Estimation | Project | 14:20 | 16:45 | 2:25 | TOTAL | 11:10
| Evening Break | Lunch and Break | 16:45 | 17:00 | 0:15
| Explored on angular | Exploration | 17:00 | 17:45 | 0:45
| Team dicussion on Web API and Work split | Meeting | 17:45 | 18:00 | 0:15
| Explored on angular | Exploration | 21:15 | 22:00 | 0:45
0:00
0:00
0:00

## 02-05-2022
Resource | Task Name | Task Type | Start Time | End Time | Total Time
Brindha | College review | Non Project | 10:30 | 12:30 | 2:00 | Split | Time | Project
| Lunch | Lunch and Break | 12:30 | 13:15 | 0:45 | Project | 6:10 | Non Project
| Modified Personal details page(HTML) | Project | 13:15 | 16:45 | 3:30 | Non Project | 2:00 | Exploration
| Evening Break | Lunch and Break | 16:45 | 17:15 | 0:30 | Exploration | 0:00 | Meeting
| Worked on sample Web api(Services) | Project | 17:20 | 20:00 | 2:40 | Meeting | 0:00 | Customer Review
[5 empty] | 0:00 | Customer Review | 0:00 | Lunch and Break
[5 empty] | 0:00 | Lunch and Break | 1:15
[5 empty] | 0:00 | TOTAL | 9:25
0:00
0:00
0:00
0:00
0:00
0:00
0:00
Chitrarasu | Wizard method HTML completed | Project | 8:30 | 10:50 | 2:20 | Split | Time
| Explored on Angular(components) | Exploration | 12:00 | 13:00 | 1:00 | Project | 6:20
| Team Meeting | Meeting | 14:00 | 14:30 | 0:30 | Non Project | 4:00
| Worked on Angular(components) | Project | 18:00 | 20:00 | 2:00 | Exploration | 1:00
| College project | Non Project | 10:00 | 14:00 | 4:00 | Meeting | 0:30
| Worked on Skill and Achievement page in wizard | Project | 15:00 | 17:00 | 2:00 | Customer Review | 0:00
[5 empty] | 0:00 | Lunch and Break | 0:00
[5 empty] | 0:00 | TOTAL | 11:50
0:00
0:00
0:00
0:00
0:00
0:00
Gugan | Entering Timesheet | Project | 9:00 | 9:15 | 0:15 | Split | Time
| Exploration on Angular topics | Exploration | 9:30 | 10:30 | 1:00 | Project | 5:25
| Morning Break | Lunch and Break | 10:30 | 11:15 | 0:45 | Non Project | 1:30
| Worked on Web api (Creating models) | Project | 11:20 | 12:20 | 1:00 | Exploration | 2:00
| Worked on Web api (Master data) | Project | 12:20 | 14:00 | 1:40 | Meeting | 0:30
| Team Meeting | Meeting | 14:00 | 14:30 | 0:30 | Customer Review | 0:00
| Lunch | Lunch and Break | 14:30 | 15:15 | 0:45 | Lunch and Break | 2:00
| Worked on College project | Non Project | 16:00 | 17:30 | 1:30 | TOTAL | 11:25
| Exploration on web API | Exploration | 17:40 | 18:40 | 1:00
| Refining errors in web api | Project | 19:00 | 20:00 | 1:00
| Working on Web api models | Project | 18:30 | 20:00 | 1:30
| Dinner | Lunch and Break | 21:30 | 22:00 | 0:30
0:00
0:00
0:00
Harini | Explored on Angular(components) | Exploration | 10:00 | 11:00 | 1:00 | Split | Time
| Modified Html layout | Project | 11:15 | 13:00 | 1:45 | Project | 2:45
| Worked on Angular(components) | Project | 13:00 | 14:00 | 1:00 | Non Project | 3:30
| Team Meeting | Meeting | 14:00 | 14:30 | 0:30 | Exploration | 1:00
| College project | Non Project | 15:30 | 19:00 | 3:30 | Meeting | 0:30
[5 empty] | 0:00 | Customer Review | 0:00
[5 empty] | 0:00 | Lunch and Break | 0:00
[5 empty] | 0:00 | TOTAL | 7:45
0:00
0:00
0:00
0:00
0:00
0:00
Kishore | Modified on HTML (achivements) | Project | 10:00 | 11:30 | 1:30 | Split | Time
| Explored Anugular Concept | Exploration | 11:30 | 12:40 | 1:10 | Project | 5:10
| Modified on HTML page(wizard) | Project | 12:50 | 14:00 | 1:10 | Non Project | 0:00
| Team Meeting | Meeting | 14:00 | 14:30 | 0:30 | Exploration | 2:10
| Lunch | Lunch and Break | 14:30 | 15:00 | 0:30 | Meeting | 0:30
| Worked on Angular topics | Project | 15:00 | 16:30 | 1:30 | Customer Review | 0:00
| Modifications on HTML layout Page(Home page) | Project | 16:30 | 17:30 | 1:00 | Lunch and Break | 0:30
| Explored on Web Api | Exploration | 17:30 | 18:30 | 1:00 | TOTAL | 8:20
0:00
0:00
0:00
0:00
0:00
0:00
0:00
Nagaraj | Modifying MyProfile page | Project | 8:45 | 9:30 | 0:45 | Split | Time
| Morning Break | Lunch and Break | 10:30 | 11:00 | 0:30 | Project | 5:30
| Modifying MyProfile page | Project | 11:00 | 12:00 | 1:00 | Non Project | 1:20
| Timesheet Entering | Non Project | 12:00 | 12:30 | 0:30 | Exploration | 0:00
| Modifying MyProfile page | Project | 14:00 | 15:00 | 1:00 | Meeting | 0:15
| Modifying create Page | Project | 15:00 | 15:45 | 0:45 | Customer Review | 0:00
| Break | Lunch and Break | 16:00 | 16:30 | 0:30 | Lunch and Break | 1:00
| Modifying create Page | Project | 16:30 | 17:00 | 0:30 | TOTAL | 8:05
| Team Meeting | Meeting | 17:00 | 17:15 | 0:15
| Modifying MyProfile page | Project | 21:30 | 23:00 | 1:30
| Exploration on web API | Non Project | 23:00 | 23:50 | 0:50
0:00
0:00
0:00
0:00
Ramakrishna | WebAPI | Project | 13:30 | 16:45 | 3:15 | Split | Time
|  |  | 0:00 | 0:00 | 0:00 | Project | 3:15
|  |  | 0:00 | 0:00 | 0:00 | Non Project | 0:00
|  |  | 0:00 | 0:00 | 0:00 | Exploration | 0:00
|  |  | 0:00 | 0:00 | 0:00 | Meeting | 0:00
|  |  | 0:00 | 0:00 | 0:00 | Customer Review | 0:00
|  |  | 0:00 | 0:00 | 0:00 | Lunch and Break | 0:00
|  |  | 0:00 | 0:00 | 0:00 | TOTAL | 3:15
|  |  | 0:00 | 0:00 | 0:00
|  |  | 0:00 | 0:00 | 0:00
|  |  | 0:00 | 0:00 | 0:00
0:00
0:00
0:00
0:00
Sekhar | Team Meeting | Project | 0:00 | 0:00 | 0:00 | Split | Time
| Soft Skill | Non Project | 0:00 | 0:00 | 0:00 | Project | 0:00
| Customer Meeting | Project | 0:00 | 0:00 | 0:00 | Non Project | 0:00
| Soft Skill | Non Project | 0:00 | 0:00 | 0:00 | Exploration | 0:00
| Lunch | Lunch and Break | 0:00 | 0:00 | 0:00 | Meeting | 0:00
| Morning Break | Lunch and Break | 0:00 | 0:00 | 0:00 | Customer Review | 0:00
| Evening Break | Lunch and Break | 0:00 | 0:00 | 0:00 | Lunch and Break | 0:00
| Learned Angular <Topics> | Project | 0:00 | 0:00 | 0:00 | TOTAL | 0:00
| Working on HTML layout | Project | 0:00 | 0:00 | 0:00
0:00
0:00
0:00
0:00
0:00
0:00
Yoga dharshini | Explored Web API, Angular | Exploration | 10:00 | 12:00 | 2:00 | Split | Time
| Lunch Break | Lunch and Break | 13:00 | 13:50 | 0:50 | Project | 4:45
| Team discussion on Web API | Meeting | 14:00 | 14:30 | 0:30 | Non Project | 0:00
| Integrated HTML Layout | Project | 14:30 | 17:00 | 2:30 | Exploration | 2:00
| Evening Break | Lunch and Break | 17:00 | 18:00 | 1:00 | Meeting | 0:30
| Worked on Web API for master services | Project | 19:45 | 22:00 | 2:15 | Customer Review | 0:00
[5 empty] | 0:00 | Lunch and Break | 1:50
[5 empty] | 0:00 | TOTAL | 9:05
0:00
0:00
0:00
0:00
0:00
0:00
0:00

## 03-05-2022
Resource | Task Name | Task Type | Start Time | End Time | Total Time
Brindha | Worked on sample web api(Models and Dbcontext) | Project | 10:00 | 12:30 | 2:30 | Split | Time | Project
| Team Meeting | Meeting | 12:30 | 13:30 | 1:00 | Project | 6:10 | Non Project
| Lunch | Lunch and Break | 13:30 | 14:00 | 0:30 | Non Project | 0:00 | Exploration
| Modified personal details page(HTML) | Project | 14:00 | 16:40 | 2:40 | Exploration | 1:00 | Meeting
| Reviewed HTML layouts | Project | 17:00 | 18:00 | 1:00 | Meeting | 1:00 | Customer Review
| Explored on angular | Exploration | 18:00 | 19:00 | 1:00 | Customer Review | 0:00 | Lunch and Break
[5 empty] | 0:00 | Lunch and Break | 0:30
[5 empty] | 0:00 | TOTAL | 8:40
0:00
0:00
0:00
0:00
0:00
0:00
0:00
Chitrarasu | Explored on angular | Exploration | 9:30 | 11:30 | 2:00 | Split | Time
| Team Meeting for Angular | Meeting | 14:00 | 14:30 | 0:30 | Project | 6:00
| Worked on angular page for sidebar, topbar, change password and profile history | Project | 15:30 | 20:00 | 4:30 | Non Project | 0:00
| Reviewed User creation services | Project | 12:00 | 13:30 | 1:30 | Exploration | 2:00
[5 empty] | 0:00 | Meeting | 0:30
[5 empty] | 0:00 | Customer Review | 0:00
[5 empty] | 0:00 | Lunch and Break | 0:00
[5 empty] | 0:00 | TOTAL | 8:30
0:00
0:00
0:00
0:00
0:00
0:00
Gugan | Entering Timesheet & Refining Errors in Migration | Project | 9:00 | 10:20 | 1:20 | Split | Time
| Morning Break | Lunch and Break | 10:30 | 11:00 | 0:30 | Project | 5:40
| College project work | Non Project | 11:10 | 16:00 | 4:50 | Non Project | 4:50
| Evening Break | Lunch and Break | 16:15 | 16:40 | 0:25 | Exploration | 0:00
| Discussed on Web Api(Services & Models) | Project | 17:00 | 17:40 | 0:40 | Meeting | 0:00
| Exploration on web API | Project | 18:00 | 19:40 | 1:40 | Customer Review | 0:00
| Working on Web Api(Understanding controllers ) | Project | 20:00 | 22:00 | 2:00 | Lunch and Break | 0:55
[5 empty] | 0:00 | TOTAL | 11:25
0:00
0:00
0:00
0:00
0:00
0:00
0:00
Harini | Explored on Angular topics(components) | Exploration | 9:00 | 10:30 | 1:30 | Split | Time
| Worked on the angular topics explored | Project | 10:40 | 13:00 | 2:20 | Project | 6:15
| Team Meeting for Angular | Meeting | 14:00 | 14:30 | 0:30 | Non Project | 0:00
| Modified the changes discussed in HTML | Project | 15:35 | 18:00 | 2:25 | Exploration | 1:30
| Worked on Angular for home page content | Project | 20:00 | 21:30 | 1:30 | Meeting | 0:30
[5 empty] | 0:00 | Customer Review | 0:00
[5 empty] | 0:00 | Lunch and Break | 0:00
[5 empty] | 0:00 | TOTAL | 8:15
0:00
0:00
0:00
0:00
0:00
0:00
Kishore | Worked on HTML page(Education Page) | Project | 9:00 | 11:10 | 2:10 | Split | Time
| Modified layput for change password(side bar) | Project | 11:10 | 13:00 | 1:50 | Project | 6:30
| Team meeting for Angular | Meeting | 14:00 | 14:30 | 0:30 | Non Project | 0:00
| Modified the layout for sidebar | Project | 11:30 | 12:50 | 1:20 | Exploration | 1:00
| Explored Angular conpects | Exploration | 13:50 | 14:50 | 1:00 | Meeting | 0:30
| Modified the cards layout Responsive | Project | 14:50 | 16:00 | 1:10 | Customer Review | 0:00
[5 empty] | 0:00 | Lunch and Break | 0:00
[5 empty] | 0:00 | TOTAL | 8:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
Nagaraj | Modifying MyProfile page | Project | 8:45 | 9:30 | 0:45 | Split | Time
| Morning Break | Lunch and Break | 10:30 | 11:00 | 0:30 | Project | 4:30
| Modifying MyProfile page | Project | 11:00 | 12:00 | 1:00 | Non Project | 0:50
| Modifying create Page | Project | 15:00 | 15:45 | 0:45 | Exploration | 0:00
| Break | Lunch and Break | 16:00 | 16:30 | 0:30 | Meeting | 0:30
| Modifying create Page | Project | 16:30 | 17:00 | 0:30 | Customer Review | 0:00
| Team Meeting | Meeting | 17:00 | 17:30 | 0:30 | Lunch and Break | 1:00
| Modifying MyProfile page | Project | 21:30 | 23:00 | 1:30 | TOTAL | 6:50
| Exploration on web API | Non Project | 23:00 | 23:50 | 0:50
0:00
0:00
Ramakrishna | WebAPI | Project | 9:00 | 11:00 | 2:00 | Split | Time
| Morning Break | Lunch and Break | 11:00 | 11:50 | 0:50 | Project | 4:00
| WebAPI | Project | 12:00 | 14:00 | 2:00 | Non Project | 0:00
|  |  | 0:00 | 0:00 | 0:00 | Exploration | 0:00
|  |  | 0:00 | 0:00 | 0:00 | Meeting | 0:00
|  |  | 0:00 | 0:00 | 0:00 | Customer Review | 0:00
|  |  | 0:00 | 0:00 | 0:00 | Lunch and Break | 0:50
|  |  | 0:00 | 0:00 | 0:00 | TOTAL | 4:50
|  |  | 0:00 | 0:00 | 0:00
|  |  | 0:00 | 0:00 | 0:00
|  |  | 0:00 | 0:00 | 0:00
0:00
0:00
0:00
0:00
Sekhar | Team Meeting | Project | 0:00 | 0:00 | 0:00 | Split | Time
| Soft Skill | Non Project | 0:00 | 0:00 | 0:00 | Project | 0:00
| Customer Meeting | Project | 0:00 | 0:00 | 0:00 | Non Project | 0:00
| Soft Skill | Non Project | 0:00 | 0:00 | 0:00 | Exploration | 0:00
| Lunch | Lunch and Break | 0:00 | 0:00 | 0:00 | Meeting | 0:00
| Morning Break | Lunch and Break | 0:00 | 0:00 | 0:00 | Customer Review | 0:00
| Evening Break | Lunch and Break | 0:00 | 0:00 | 0:00 | Lunch and Break | 0:00
| Learned Angular <Topics> | Project | 0:00 | 0:00 | 0:00 | TOTAL | 0:00
| Working on HTML layout | Project | 0:00 | 0:00 | 0:00
0:00
0:00
0:00
0:00
0:00
0:00
Yoga dharshini | Explored Angular basic conpects | Exploration | 11:00 | 12:00 | 1:00 | Split | Time
| Lunch Break | Lunch and Break | 13:00 | 13:50 | 0:50 | Project | 6:15
| Team Discussion on Angular | Meeting | 14:00 | 14:30 | 0:30 | Non Project | 0:00
| Integrated HTML Layout | Project | 14:30 | 18:00 | 3:30 | Exploration | 1:00
| Worked on Angular Concepts | Project | 18:15 | 21:00 | 2:45 | Meeting | 0:30
[5 empty] | 0:00 | Customer Review | 0:00
[5 empty] | 0:00 | Lunch and Break | 0:50
[5 empty] | 0:00 | TOTAL | 8:35
0:00
0:00
0:00
0:00
0:00
0:00
0:00

## 04-05-2022
Resource | Task Name | Task Type | Start Time | End Time | Total Time
Brindha | Explored on Web api | Project | 8:30 | 10:30 | 2:00 | Split | Time | Project
| Morning Break | Lunch and Break | 10:30 | 10:45 | 0:15 | Project | 7:15 | Non Project
| Worked on Web api (Models and Dbcontext) -College master data | Project | 10:45 | 11:00 | 0:15 | Non Project | 0:00 | Exploration
| Worked on Web api(Datafactory and Controllers) | Project | 11:00 | 13:00 | 2:00 | Exploration | 1:10 | Meeting
| Lunch | Lunch and Break | 13:00 | 13:45 | 0:45 | Meeting | 0:35 | Customer Review
| Worked on Web api(Services and DataAccessLayer) | Project | 13:45 | 15:45 | 2:00 | Customer Review | 0:00 | Lunch and Break
| Evening Break | Lunch and Break | 15:45 | 16:00 | 0:15 | Lunch and Break | 1:15
| Angular session | Exploration | 16:00 | 17:10 | 1:10 | TOTAL | 10:15
| Team Meeting(Webapi and html layouts) | Meeting | 17:25 | 18:00 | 0:35
| Worked on Web Api(Models- Userservices) | Project | 20:30 | 21:30 | 1:00
0:00
0:00
0:00
0:00
0:00
Chitrarasu | Explored on angular topics (interpolation and binding) | Project | 8:30 | 10:00 | 1:30 | Split | Time
| Morning Break | Lunch and Break | 10:00 | 10:20 | 0:20 | Project | 7:05
| Worked on interpolation | Project | 10:30 | 13:00 | 2:30 | Non Project | 0:00
| Lunch | Lunch and Break | 13:00 | 13:40 | 0:40 | Exploration | 1:15
| Worked on binding | Project | 13:40 | 15:45 | 2:05 | Meeting | 0:35
| Evening Break | Lunch and Break | 15:45 | 16:00 | 0:15 | Customer Review | 0:00
| Angular session | Exploration | 16:00 | 17:15 | 1:15 | Lunch and Break | 1:15
| Team meeting | Meeting | 17:25 | 18:00 | 0:35 | TOTAL | 10:10
| Worked on angular for createprofile | Project | 19:00 | 20:00 | 1:00
0:00
0:00
0:00
0:00
0:00
Gugan | Worked on Web Api(Controllers) | Project | 8:40 | 10:00 | 1:20 | Split | Time
| Entering Timesheet | Project | 10:10 | 10:25 | 0:15 | Project | 7:10
| Morning Break | Lunch and Break | 10:30 | 10:45 | 0:15 | Non Project | 0:00
| Modifications on Web API(Master data - College) | Project | 10:50 | 12:40 | 1:50 | Exploration | 1:15
| Lunch | Lunch and Break | 13:00 | 13:30 | 0:30 | Meeting | 0:35
| Worked on Web api (Models and Dbcontext - College service) | Project | 13:30 | 15:30 | 2:00 | Customer Review | 0:00
| Evening Break | Lunch and Break | 15:40 | 16:00 | 0:20 | Lunch and Break | 1:05
| Angular Session with TN Team | Exploration | 16:00 | 17:15 | 1:15 | TOTAL | 10:05
| Team Meeting | Meeting | 17:25 | 18:00 | 0:35
| Working on Web api models(Refining Errors in Migration) | Project | 19:15 | 21:00 | 1:45
0:00
0:00
0:00
0:00
0:00
Harini | Learned Angular topics for sidebar and tried it | Project | 8:30 | 10:00 | 1:30 | Split | Time
| Morning Break | Lunch and Break | 10:00 | 10:20 | 0:20 | Project | 6:05
| Tried out studied concepts of angular in the project | Project | 10:30 | 13:00 | 2:30 | Non Project | 0:00
| Lunch | Lunch and Break | 13:10 | 13:30 | 0:20 | Exploration | 1:15
| Worked on angular concepts for sidebar and navbar | Project | 13:40 | 15:45 | 2:05 | Meeting | 0:35
| Evening Break | Lunch and Break | 15:45 | 16:00 | 0:15 | Customer Review | 0:00
| Angular session | Exploration | 16:00 | 17:15 | 1:15 | Lunch and Break | 0:55
| Team meeting | Meeting | 17:25 | 18:00 | 0:35 | TOTAL | 8:50
0:00
0:00
0:00
0:00
0:00
0:00
Kishore | worked on sample application in angular | Project | 8:30 | 10:30 | 2:00 | Split | Time
| Worked on angular topics Explored | Project | 10:30 | 11:50 | 1:20 | Project | 6:10
| Morning Break | Lunch and Break | 11:50 | 12:10 | 0:20 | Non Project | 0:00
| Modified the cards layout(side bar) | Project | 12:10 | 13:30 | 1:20 | Exploration | 1:15
| Lunch | Lunch and Break | 13:30 | 14:00 | 0:30 | Meeting | 1:10
| Modified the Profile Histroy layout(side bar) | Project | 14:00 | 15:30 | 1:30 | Customer Review | 0:00
| Evening Break | Lunch and Break | 15:30 | 16:00 | 0:30 | Lunch and Break | 1:20
| Angular Session with TN Team | Exploration | 16:00 | 17:15 | 1:15 | TOTAL | 9:55
| Team Meeting | Meeting | 17:10 | 18:20 | 1:10
0:00
0:00
0:00
0:00
0:00
0:00
Nagaraj | WebAPI exploration | Exploration | 8:45 | 10:00 | 1:15 | Split | Time
| worked on API | Project | 10:10 | 10:30 | 0:20 | Project | 5:35
| Morning Break | Lunch and Break | 10:30 | 11:00 | 0:30 | Non Project | 0:00
| Worked on webAPI | Project | 11:15 | 12:30 | 1:15 | Exploration | 4:15
| lunch | Lunch and Break | 13:00 | 14:00 | 1:00 | Meeting | 0:30
| Team Meeting | Meeting | 12:30 | 13:00 | 0:30 | Customer Review | 0:00
| worked on webAPI | Project | 14:00 | 16:00 | 2:00 | Lunch and Break | 1:30
| Exploration on Web api | Exploration | 18:00 | 20:00 | 2:00 | TOTAL | 11:50
| Modifications on My profile page responsiveness | Project | 21:00 | 23:00 | 2:00
| Angular session | Exploration | 16:00 | 17:00 | 1:00
0:00
0:00
Ramakrishna | WebAPI | Project | 9:00 | 11:00 | 2:00 | Split | Time
| Morning Break | Lunch and Break | 11:00 | 11:50 | 0:50 | Project | 4:00
| WebAPI | Project | 12:00 | 14:00 | 2:00 | Non Project | 0:00
|  |  | 0:00 | 0:00 | 0:00 | Exploration | 0:00
|  |  | 0:00 | 0:00 | 0:00 | Meeting | 0:00
|  |  | 0:00 | 0:00 | 0:00 | Customer Review | 0:00
|  |  | 0:00 | 0:00 | 0:00 | Lunch and Break | 0:50
|  |  | 0:00 | 0:00 | 0:00 | TOTAL | 4:50
|  |  | 0:00 | 0:00 | 0:00
|  |  | 0:00 | 0:00 | 0:00
|  |  | 0:00 | 0:00 | 0:00
0:00
0:00
0:00
0:00
Sekhar | Team Meeting | Project | 0:00 | 0:00 | 0:00 | Split | Time
| Soft Skill | Non Project | 0:00 | 0:00 | 0:00 | Project | 0:00
| Customer Meeting | Project | 0:00 | 0:00 | 0:00 | Non Project | 0:00
| Soft Skill | Non Project | 0:00 | 0:00 | 0:00 | Exploration | 0:00
| Lunch | Lunch and Break | 0:00 | 0:00 | 0:00 | Meeting | 0:00
| Morning Break | Lunch and Break | 0:00 | 0:00 | 0:00 | Customer Review | 0:00
| Evening Break | Lunch and Break | 0:00 | 0:00 | 0:00 | Lunch and Break | 0:00
| Learned Angular <Topics> | Project | 0:00 | 0:00 | 0:00 | TOTAL | 0:00
| Working on HTML layout | Project | 0:00 | 0:00 | 0:00
0:00
0:00
0:00
0:00
0:00
0:00
Yoga dharshini | Updated timesheet and pushed in GIT | Project | 8:30 | 9:30 | 1:00 | Split | Time
| Explored typescript, components, interpolation | Project | 9:30 | 10:20 | 0:50 | Project | 6:15
| Morning Break | Lunch and Break | 10:20 | 10:40 | 0:20 | Non Project | 1:15
| Implemented angular concepts and created sample components | Project | 10:40 | 13:00 | 2:20 | Exploration | 1:30
| Lunch Break | Lunch and Break | 13:00 | 13:30 | 0:30 | Meeting | 0:45
| Worked on angular concepts for sidebar and navbar | Project | 13:40 | 15:45 | 2:05 | Customer Review | 0:00
| Evening Break | Lunch and Break | 15:45 | 16:00 | 0:15 | Lunch and Break | 1:05
| Angular Session with TN Team | Non Project | 16:00 | 17:15 | 1:15 | TOTAL | 10:50
| Team meeting | Meeting | 17:15 | 18:00 | 0:45
| Explored on Databinding | Exploration | 21:00 | 22:30 | 1:30
0:00
0:00
0:00
0:00
0:00

## 05-05-2022
Resource | Task Name | Task Type | Start Time | End Time | Total Time
Brindha | Updated Timesheet | Project | 8:45 | 9:10 | 0:25 | Split | Time | Project
| Worked on Web Api(Userservices - Models and Dbcontext) | Project | 9:10 | 10:45 | 1:35 | Project | 7:10 | Non Project
| Morning Break | Lunch and Break | 10:45 | 11:00 | 0:15 | Non Project | 0:00 | Exploration
| Worked on Web api(Datafactory) | Project | 11:00 | 11:30 | 0:30 | Exploration | 1:15 | Meeting
| Angular session | Exploration | 11:30 | 12:45 | 1:15 | Meeting | 0:20 | Customer Review
| lunch | Lunch and Break | 12:45 | 13:45 | 1:00 | Customer Review | 0:00 | Lunch and Break
| Team Meeting | Meeting | 14:10 | 14:30 | 0:20 | Lunch and Break | 1:45
| Worked on Web Api(logger) | Project | 14:30 | 16:00 | 1:30 | TOTAL | 10:30
| Evening Break | Lunch and Break | 16:00 | 16:30 | 0:30
| Worked on Web api (Exceptions) | Project | 16:30 | 18:10 | 1:40
| Worked on Web api(master data - Domain) | Project | 19:00 | 20:30 | 1:30
0:00
0:00
0:00
0:00
Chitrarasu | Worked on angular for view profile | Project | 8:30 | 10:30 | 2:00 | Split | Time
| Morning Break | Lunch and Break | 10:30 | 11:00 | 0:30 | Project | 7:10
| Worked on angular for creating path | Project | 11:10 | 11:40 | 0:30 | Non Project | 0:00
| Angular session | Exploration | 11:40 | 12:45 | 1:05 | Exploration | 1:05
| Lunch | Lunch and Break | 13:00 | 14:00 | 1:00 | Meeting | 0:20
| Exploration on integration of angular pages | Project | 14:10 | 16:00 | 1:50 | Customer Review | 0:00
| Evening Break | Lunch and Break | 16:00 | 16:30 | 0:30 | Lunch and Break | 2:00
| Team Meeting | Meeting | 16:40 | 17:00 | 0:20 | TOTAL | 10:35
| Worked on integartion of angular pages | Project | 17:00 | 19:50 | 2:50
0:00
0:00
0:00
Gugan | Discussed with teammates on yesterday's progress(web api) | Project | 8:50 | 9:40 | 0:50 | Split | Time
| Entering Timesheet | Project | 9:40 | 10:00 | 0:20 | Project | 6:45
| Morning Break | Lunch and Break | 10:30 | 10:45 | 0:15 | Non Project | 0:00
| Worked on Web api (Exceptions) | Project | 10:50 | 11:40 | 0:50 | Exploration | 2:10
| Angular session | Exploration | 11:40 | 12:45 | 1:05 | Meeting | 0:20
| Lunch | Lunch and Break | 13:00 | 13:55 | 0:55 | Customer Review | 0:00
| Team Meeting | Meeting | 14:10 | 14:30 | 0:20 | Lunch and Break | 1:30
| Exploration on Angular (Interpolation and binding) | Exploration | 14:40 | 15:45 | 1:05 | TOTAL | 10:45
| Evening Break | Lunch and Break | 16:00 | 16:20 | 0:20
| Worked on Web api(master data - Domain) | Project | 16:30 | 18:00 | 1:30
| Refining User service on Web api | Project | 18:30 | 20:00 | 1:30
| Worked on Web api (College and Domain) | Project | 20:00 | 21:45 | 1:45
0:00
0:00
0:00
Harini | Worked on angular for home page | Project | 8:45 | 10:30 | 1:45 | Split | Time
| Morning Break | Lunch and Break | 10:30 | 11:00 | 0:30 | Project | 7:15
| Worked on Angular for adding of image and icons | Project | 11:10 | 11:40 | 0:30 | Non Project | 0:00
| Angular session | Exploration | 11:40 | 12:45 | 1:05 | Exploration | 1:05
| Lunch | Lunch and Break | 13:00 | 14:00 | 1:00 | Meeting | 0:20
| Team meeting | Meeting | 14:10 | 14:30 | 0:20 | Customer Review | 0:00
| Explored on routing between components in angular | Project | 14:30 | 16:15 | 1:45 | Lunch and Break | 1:45
| Evening Break | Lunch and Break | 16:15 | 16:30 | 0:15 | TOTAL | 10:25
| Worked on Integration of Html pages | Project | 16:30 | 18:00 | 1:30
| Worked on Angular | Project | 21:00 | 22:45 | 1:45
0:00
0:00
0:00
0:00
Kishore | worked on sample application in angular | Exploration | 9:00 | 10:30 | 1:30 | Split | Time
| Exploration on angular topics | Project | 10:30 | 11:00 | 0:30 | Project | 3:05
| Break | Lunch and Break | 11:00 | 11:30 | 0:30 | Non Project | 3:45
| Angular session | Non Project | 11:30 | 12:50 | 1:20 | Exploration | 1:30
| Lunch Break | Lunch and Break | 12:50 | 13:30 | 0:40 | Meeting | 0:20
| Exploration for Project review(college) | Non Project | 13:30 | 14:55 | 1:25 | Customer Review | 0:00
| Team Meeting | Meeting | 14:10 | 14:30 | 0:20 | Lunch and Break | 1:40
| Meeting for Project review(College) | Non Project | 15:00 | 16:00 | 1:00 | TOTAL | 10:20
| Break | Lunch and Break | 16:00 | 16:30 | 0:30
| Worked on HTML layout(HR home page) | Project | 16:00 | 17:50 | 1:50
| Worked on HTML layout(Admin home Page) | Project | 17:15 | 18:00 | 0:45
0:00
0:00
0:00
0:00
0:00
Nagaraj | WebAPI | Project | 8:45 | 10:30 | 1:45 | Split | Time
| Morning Break | Lunch and Break | 10:30 | 11:00 | 0:30 | Project | 7:30
| WebAPI | Project | 11:00 | 12:00 | 1:00 | Non Project | 0:00
| webAPI exploration | Exploration | 12:00 | 12:30 | 0:30 | Exploration | 1:20
| Modifying MyProfile page | Project | 13:30 | 15:00 | 1:30 | Meeting | 0:15
| Modifying create Page | Project | 15:00 | 15:45 | 0:45 | Customer Review | 0:00
| Break | Lunch and Break | 16:00 | 16:30 | 0:30 | Lunch and Break | 1:00
| Modifying create Page | Project | 16:30 | 17:30 | 1:00 | TOTAL | 10:05
| Team Meeting | Meeting | 17:30 | 17:45 | 0:15
| Modifying MyProfile page | Project | 21:30 | 23:00 | 1:30
| Exploration on web API | Exploration | 23:00 | 23:50 | 0:50
0:00
0:00
|  | Project | 8:30 | 8:45 | 0:15
|  | Project | 8:45 | 9:30 | 0:45
Ramakrishna | WebAPI | Project | 9:00 | 11:00 | 2:00 | Split | Time
| Morning Break | Lunch and Break | 11:00 | 11:50 | 0:50 | Project | 5:10
| WebAPI | Project | 12:00 | 13:30 | 1:30 | Non Project | 0:00
| WebAPI | Project | 13:30 | 14:10 | 0:40 | Exploration | 0:00
| Lunch Break | Lunch and Break | 14:10 | 15:00 | 0:50 | Meeting | 0:00
|  |  | 0:00 | 0:00 | 0:00 | Customer Review | 0:00
|  |  | 0:00 | 0:00 | 0:00 | Lunch and Break | 1:40
|  |  | 0:00 | 0:00 | 0:00 | TOTAL | 6:50
|  |  | 0:00 | 0:00 | 0:00
0:00
0:00
0:00
0:00
|  | Project | 0:00 | 0:00 | 0:00
|  | Non Project | 0:00 | 0:00 | 0:00
Sekhar | Team Meeting | Project | 0:00 | 0:00 | 0:00 | Split | Time
| Soft Skill | Non Project | 0:00 | 0:00 | 0:00 | Project | 0:00
| Customer Meeting | Lunch and Break | 0:00 | 0:00 | 0:00 | Non Project | 0:00
| Soft Skill | Lunch and Break | 0:00 | 0:00 | 0:00 | Exploration | 0:00
| Lunch | Lunch and Break | 0:00 | 0:00 | 0:00 | Meeting | 0:00
| Morning Break | Project | 0:00 | 0:00 | 0:00 | Customer Review | 0:00
| Evening Break | Project | 0:00 | 0:00 | 0:00 | Lunch and Break | 0:00
| Learned Angular <Topics> |  |  |  | 0:00 | TOTAL | 0:00
| Working on HTML layout |  |  |  | 0:00
0:00
0:00
0:00
0:00
0:00
0:00
Yoga dharshini | Updated timesheet and pushed in GIT | Project | 8:30 | 9:30 | 1:00 | Split | Time
| Explored Databinding | Exploration | 9:30 | 10:45 | 1:15 | Project | 7:30
| Morning Break | Lunch and Break | 10:45 | 11:00 | 0:15 | Non Project | 1:05
| Implemented and created components for login,changepassword | Project | 11:00 | 11:40 | 0:40 | Exploration | 1:15
| Angular session with TN team | Non Project | 11:40 | 12:45 | 1:05 | Meeting | 0:45
| Lunch Break | Lunch and Break | 12:45 | 13:30 | 0:45 | Customer Review | 0:00
| Worked on angular for forgotpassword component | Project | 13:30 | 15:45 | 2:15 | Lunch and Break | 1:15
| Evening Break | Lunch and Break | 15:45 | 16:00 | 0:15 | TOTAL | 11:50
| Worked on interpolation in angular | Project | 16:15 | 18:00 | 1:45
| Team meeting | Meeting | 17:15 | 18:00 | 0:45
| Worked on angular routing | Project | 20:40 | 22:30 | 1:50
0:00
0:00
0:00
0:00

## 06-05-2022
Resource | Task Name | Task Type | Start Time | End Time | Total Time
Brindha | Updated Timesheet | Project | 8:45 | 9:10 | 0:25 | Split | Time | Project
| Worked on Web Api(Userservices - Models and Dbcontext) | Project | 9:10 | 10:45 | 1:35 | Project | 7:10 | Non Project
| Morning Break | Lunch and Break | 10:45 | 11:00 | 0:15 | Non Project | 0:00 | Exploration
| Worked on Web api(Datafactory) | Project | 11:00 | 11:30 | 0:30 | Exploration | 1:15 | Meeting
| Angular session | Exploration | 11:30 | 12:45 | 1:15 | Meeting | 0:20 | Customer Review
| lunch | Lunch and Break | 12:45 | 13:45 | 1:00 | Customer Review | 0:00 | Lunch and Break
| Team Meeting | Meeting | 14:10 | 14:30 | 0:20 | Lunch and Break | 1:45
| Worked on Web Api(logger) | Project | 14:30 | 16:00 | 1:30 | TOTAL | 10:30
| Evening Break | Lunch and Break | 16:00 | 16:30 | 0:30
| Worked on Web api (Exceptions) | Project | 16:30 | 18:10 | 1:40
| Worked on Web api(master data - Domain) | Project | 19:00 | 20:30 | 1:30
0:00
0:00
0:00
0:00
Chitrarasu | Created Angular pages with the use of components | Project | 8:30 | 10:30 | 2:00 | Split | Time
| Morning Break | Lunch and Break | 10:30 | 11:00 | 0:30 | Project | 6:05
| Created path to all pages | Project | 11:00 | 12:40 | 1:40 | Non Project | 0:00
| Lunch | Lunch and Break | 13:00 | 13:50 | 0:50 | Exploration | 2:30
| Customer Meeting | Customer Review | 14:00 | 15:30 | 1:30 | Meeting | 0:25
| Angular session | Exploration | 16:00 | 17:00 | 1:00 | Customer Review | 1:30
| Evening Break | Lunch and Break | 17:10 | 17:30 | 0:20 | Lunch and Break | 1:40
| Team Meeting | Meeting | 17:35 | 18:00 | 0:25 | TOTAL | 12:10
| Worked on view pages(Card view Page) | Project | 18:05 | 20:30 | 2:25
| Explored on integration of Web API and Angular. | Exploration | 22:00 | 23:30 | 1:30
0:00
0:00
Gugan | Worked on Web api (College and Domain Service) | Project | 8:30 | 9:40 | 1:10 | Split | Time
| Entering Timesheet | Project | 9:40 | 10:00 | 0:20 | Project | 8:00
| Morning Break | Lunch and Break | 10:30 | 10:45 | 0:15 | Non Project | 1:00
| Worked on Web api (Master Data Services) | Project | 10:50 | 12:40 | 1:50 | Exploration | 0:00
| Lunch | Lunch and Break | 13:00 | 13:45 | 0:45 | Meeting | 0:00
| Customer Meeting | Customer Review | 14:00 | 15:30 | 1:30 | Customer Review | 1:30
| Discussed about Re-work of web api(User and Master Services) | Project | 15:30 | 16:00 | 0:30 | Lunch and Break | 1:00
| Angular session | Non Project | 16:00 | 17:00 | 1:00 | TOTAL | 11:30
| Re-worked on the Modifications of Web Api(User and Master Data Services) | Project | 17:00 | 20:20 | 3:20
| Discussion and Review with Customer | Project | 20:20 | 20:40 | 0:20
| Refining Master service on Web api | Project | 21:30 | 22:00 | 0:30
0:00
0:00
0:00
0:00
Harini | Worked on routing of angular pages | Project | 8:45 | 10:30 | 1:45 | Split | Time
| Worked on Integration of Html pages | Project | 10:30 | 11:30 | 1:00 | Project | 6:25
| Worked on Angular for modified Html pages | Project | 11:40 | 13:00 | 1:20 | Non Project | 0:00
| Lunch | Lunch and Break | 13:00 | 13:50 | 0:50 | Exploration | 2:00
| Customer Meeting | Customer Review | 14:00 | 15:30 | 1:30 | Meeting | 0:25
| Angular session | Exploration | 16:00 | 17:00 | 1:00 | Customer Review | 1:30
| Evening Break | Lunch and Break | 17:10 | 17:30 | 0:20 | Lunch and Break | 1:10
| Team Meeting | Meeting | 17:35 | 18:00 | 0:25 | TOTAL | 11:30
| Worked on angular for cards view page | Project | 18:10 | 20:30 | 2:20
| Explored on pagination in angular and integration of web api and angular | Exploration | 22:00 | 23:00 | 1:00
0:00
0:00
0:00
0:00
Kishore | Worked on angular Profile Histroy Page | Project | 8:30 | 10:30 | 2:00 | Split | Time
| Worked on angular HR home page | Project | 10:30 | 11:20 | 0:50 | Project | 5:35
| Break | Lunch and Break | 11:20 | 11:30 | 0:10 | Non Project | 0:00
| Explored on angular | Exploration | 11:30 | 12:50 | 1:20 | Exploration | 4:10
| Lunch Break | Lunch and Break | 13:00 | 13:40 | 0:40 | Meeting | 0:25
| Customer Meeting | Customer Review | 14:00 | 15:30 | 1:30 | Customer Review | 1:30
| Angular session | Exploration | 16:00 | 17:00 | 1:00 | Lunch and Break | 1:20
| Break | Lunch and Break | 17:00 | 17:30 | 0:30 | TOTAL | 13:00
| Team Meeting | Meeting | 17:35 | 18:00 | 0:25
| Explored on Data Binding | Exploration | 18:00 | 19:50 | 1:50
| Worked on angular HR home page | Project | 17:15 | 17:50 | 0:35
| Worked on angular Admin home page | Project | 17:50 | 20:00 | 2:10
0:00
0:00
0:00
0:00
Nagaraj | Timesheet filling | Non Project | 8:45 | 9:15 | 0:30 | Split | Time
| HTml my Profile page | Project | 9:20 | 9:45 | 0:25 | Project | 5:00
| web API on Profile service | Project | 9:55 | 10:30 | 0:35 | Non Project | 0:30
| Break | Lunch and Break | 10:30 | 10:45 | 0:15 | Exploration | 1:30
| webAPI exploration | webAPI exploration | 10:55 | 12:30 | 1:35 | Meeting | 0:15
| Lunch | Lunch and Break | 12:30 | 13:10 | 0:40 | Customer Review | 1:30
| Customer Meeting | Customer Review | 14:00 | 15:30 | 1:30 | Lunch and Break | 0:55
| Team Meeting | Meeting | 16:15 | 16:30 | 0:15 | TOTAL | 9:40
| Angular session | Exploration | 16:30 | 17:30 | 1:00
| WebAPI on view cards page | Project | 18:00 | 20:45 | 2:45
| exploration on navigation properities | Exploration | 22:00 | 22:30 | 0:30
| WebAPI on view cards page | Project | 22:35 | 23:50 | 1:15
|  | Project | 8:30 | 8:45 | 0:15
|  | Project | 8:45 | 9:30 | 0:45
Ramakrishna | WebAPI | Project | 9:00 | 11:00 | 2:00 | Split | Time
| Morning Break | Lunch and Break | 11:00 | 11:50 | 0:50 | Project | 5:10
| WebAPI | Project | 12:00 | 13:30 | 1:30 | Non Project | 0:00
| WebAPI | Project | 13:30 | 14:10 | 0:40 | Exploration | 0:00
| Lunch Break | Lunch and Break | 14:10 | 15:00 | 0:50 | Meeting | 0:00
|  |  | 0:00 | 0:00 | 0:00 | Customer Review | 0:00
|  |  | 0:00 | 0:00 | 0:00 | Lunch and Break | 1:40
|  |  | 0:00 | 0:00 | 0:00 | TOTAL | 6:50
|  |  | 0:00 | 0:00 | 0:00
0:00
0:00
0:00
0:00
|  | Project | 0:00 | 0:00 | 0:00
|  | Non Project | 0:00 | 0:00 | 0:00
Sekhar | Team Meeting | Project | 0:00 | 0:00 | 0:00 | Split | Time
| Soft Skill | Non Project | 0:00 | 0:00 | 0:00 | Project | 0:00
| Customer Meeting | Lunch and Break | 0:00 | 0:00 | 0:00 | Non Project | 0:00
| Soft Skill | Lunch and Break | 0:00 | 0:00 | 0:00 | Exploration | 0:00
| Lunch | Lunch and Break | 0:00 | 0:00 | 0:00 | Meeting | 0:00
| Morning Break | Project | 0:00 | 0:00 | 0:00 | Customer Review | 0:00
| Evening Break | Project | 0:00 | 0:00 | 0:00 | Lunch and Break | 0:00
| Learned Angular <Topics> |  |  |  | 0:00 | TOTAL | 0:00
| Working on HTML layout |  |  |  | 0:00
0:00
0:00
0:00
0:00
0:00
0:00
Yoga dharshini | Updated timesheet | Project | 8:30 | 8:40 | 0:10 | Split | Time
| Worked on angular | Project | 8:40 | 10:40 | 2:00 | Project | 4:55
| Morning Break | Lunch and Break | 10:40 | 11:00 | 0:20 | Non Project | 1:00
| Worked on angular and web api integration | Project | 11:00 | 12:45 | 1:45 | Exploration | 2:10
| Lunch Break | Lunch and Break | 12:45 | 13:30 | 0:45 | Meeting | 0:15
| Customer Meeting | Customer Review | 14:00 | 15:30 | 1:30 | Customer Review | 2:00
| College project review | Meeting | 15:30 | 15:45 | 0:15 | Lunch and Break | 1:20
| Evening Break | Lunch and Break | 15:45 | 16:00 | 0:15 | TOTAL | 11:40
| Angular session with TN team | Non Project | 16:00 | 17:00 | 1:00
| Worked on angular and web api integration | Project | 17:00 | 18:00 | 1:00
| Explored on Data Binding | Exploration | 18:00 | 20:10 | 2:10
| Customer Meeting and Discussion | Customer Review | 20:10 | 20:40 | 0:30
0:00
0:00
0:00