## HTML_Estimation
S.No | Task | Sub Tasks | Estimation in Hrs
1 | Login | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 2
|  | HTML Validations | 1.5
|  | Web API Integration | 2
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1.5
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1.5
|  | Code Review | 2
|  | Unit Testing | 2
18.5
2 | Change password | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 2
|  | HTML Validations | 2
|  | Web API Integration | 2
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1.5
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1.5
|  | Code Review | 2
|  | Unit Testing | 2
19
3 | Forgot Password | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 2
|  | HTML Validations | 2
|  | Web API Integration | 2
|  | Web API - Service Implementation | 1.5
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 2
|  | Unit Testing | 2
17.5
4 | Home Page(Searcher,Creator,HR, Admin) | Low Level Design - Sequence Diagram | 8
|  | HTML preparation | 15
|  | Web API Integration | 8
|  | Web API - Service Implementation | 10
|  | Swagger - API Documentation | 5
|  | Service Validations , Exception and Logging | 10
|  | Code Cleanup | 5
|  | Code Review | 5
|  | Unit Testing | 7
73
5 | Results Viewing Page(Cards-approved,Declined,Waiting for approval, Total profiles) | Low Level Design - Sequence Diagram | 9
|  | HTML preparation | 17
|  | Web API Integration | 7
|  | Web API - Service Implementation | 10
|  | Swagger - API Documentation | 5
|  | Service Validations , Exception and Logging | 9
|  | Code Cleanup | 5
|  | Code Review | 6.5
|  | Unit Testing | 5.5
74
|  | Code Merging | 9
|  | Integration Testing | 7
|  | Compatibility testing | 5
|  | Deployment Documentation | 6
27
6 | Profile Viewing Page | Low Level Design - Sequence Diagram | 4
|  | HTML preparation | 5
|  | Web API Integration | 3
|  | Web API - Service Implementation | 4
|  | Swagger - API Documentation | 3
|  | Service Validations , Exception and Logging | 3
|  | Code Cleanup | 2
|  | Code Review | 3
|  | Unit Testing | 3
30
7 | Create Profile Page | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 2
|  | Web API Integration | 2
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 2
|  | Code Review | 2
|  | Unit Testing | 1
15
8 | Personal Details Entering Page | Low Level Design - Sequence Diagram | 4
|  | HTML preparation | 5
|  | HTML Validations | 6
|  | Web API Integration | 5
|  | Web API - Service Implementation | 4
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 6
|  | Code Cleanup | 3
|  | Code Review | 3
|  | Unit Testing | 3
41
9 | Education Details Page | Low Level Design - Sequence Diagram | 4
|  | HTML preparation | 5
|  | HTML Validations | 4
|  | Web API Integration | 4
|  | Web API - Service Implementation | 4
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 4
|  | Code Cleanup | 2
|  | Code Review | 3
|  | Unit Testing | 3
35
10 | Project Details Page | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 3
|  | HTML Validations | 2
|  | Web API Integration | 2
|  | Web API - Service Implementation | 4
|  | Swagger - API Documentation | 2
|  | Code Cleanup | 2
|  | Code Review | 3
|  | Unit Testing | 3
20
11 | Skills Details Page | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 2
|  | HTML Validations | 2
|  | Web API Integration | 2
|  | Web API - Service Implementation | 3
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 2
|  | Unit Testing | 2
20
12 | Achievements | Low Level Design - Sequence Diagram | 4
|  | HTML preparation | 4
|  | HTML Validations | 3
|  | Web API Integration | 3
|  | Web API - Service Implementation | 4
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 3
|  | Code Cleanup | 2
|  | Code Review | 2
|  | Unit Testing | 2
29
|  | Code Merging | 10
|  | Integration Testing | 8
|  | Compatibility testing | 5
|  | Deployment Documentation | 7
30
13 | User Creation | Low Level Design - Sequence Diagram | 3
|  | HTML preparation | 4
|  | HTML Validations | 4
|  | Web API Integration | 2
|  | Web API - Service Implementation | 3
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 3
|  | Code Cleanup | 3
|  | Code Review | 3.5
|  | Unit Testing | 2
29.5
14 | Edit User Details | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 2
|  | HTML Validations | 3
|  | Web API Integration | 2
|  | Web API - Service Implementation | 3
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 3
|  | Code Cleanup | 2
|  | Code Review | 2
|  | Unit Testing | 2
23
|  | Code Merging | 4
|  | Integration Testing | 4
|  | Compatibility testing | 5
|  | Deployment Documentation | 4
17
15 | Profile History | Low Level Design - Sequence Diagram | 4
|  | HTML preparation | 6
|  | HTML Validations | 2
|  | Web API Integration | 3
|  | Web API - Service Implementation | 4
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 4
|  | Code Cleanup | 2
|  | Code Review | 3
|  | Unit Testing | 3
33
|  | Code Merging | 3
|  | Integration Testing | 3
|  | Compatibility testing | 2
|  | Deployment Documentation | 3
11
|  | Total hours | 562.5