## 05-04-2022
Resource Name | Action Point / Impediments | Status | Comments
Harini R & Chitrarasu | finding solution for github account problem
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Harini R | Requirement refining and storing of lower hierarchy designated people | Work flow completed | How a user can view his lower hierarchy person on the system | 5 | 2
Chitrarasu V | Working to store the profile in database | User Story completed | How to show the lower profile in dashboard | 5 | 2
Sekhar | Requirement refining | User Workflow | How can store lower hierarchy on the system. | 5 | 2
Nagaraj K | Hierarchy Mapping | Workflow based on Filters | how to map the lower profiles under higher profiles | 5 | 2
Kishore kumar A N | Requirement refining | User Workflow | How to show the lower profile in dashboard | 5 | 2
Ramakrishna | Requirements and hierachy storage | User Flow for creation | How to add restrictions | 5 | 2
Brindha M | Hierarchy Mapping | User Flow for searcher | how to map hierarchy | 5 | 2
Gugan RB | Working to store the profile in database | User Story completed,User Flow for searcher | How to show the lower profile in dashboard | 5 | 2
Yoga Dharshini | What are to be maintained as master data and role mapping | Overall flow for both user | Hierarchy mapping | 5 | 2
Dinesh Kumar

## 06-04-2022
Resource Name | Action Point / Impediments | Status | Comments
Harini R & Chitrarasu | finding solution for github account problem | Completed | Signed in another user
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Brindha | Acceptance criteria for Admin | Discussion and meeting with rafi - 1hour Team Discussion- 2hours Made minor changes in user story - 1 hour Acceptance criteria for Creator and Searcher - Completed - 2hours | Acceptance criteria for Admin | 6 | 1 | Having doubt in Share feature for acceptance criteria
Chitrarasu | Exploration on Web API Assumptions | Meeting with rafi - 1 hrs Made minor changes in user story as discussed in previous meeting - 1.5 hrs Discussion with Gugan about Assumptions - 1 hrs Discussion with Gugan about Constraints - 1.5 hrs Discussion with team on admin's user story,work flow,prototype and hierarchial mapping - 2 hrs | Assumptions | 7 | 1 | Having clarity in different assumptions was difficult
Dinesh Kumar | AB | AB | AB | AB | AB | AB
Gugan | Exploration on Entity Framework Assumptions | Meeting with rafi - 1 hrs Made minor changes in user story as discussed in previous meeting - 1.5 hrs Discussion with Chitrarasu about Assumptions - 1 hrs Discussion with Chitrarasu about Constraints - 1.5 hrs Discussion with team on admin's user story,work flow,prototype and hierarchial mapping - 2 hrs | Assumptions | 7 | 1 | Having clarity in different assumptions was difficult
Harini | Creation of prototype for entering project details in the system,View page | Requirement refining - Project Details - 1hour Prototype for Register, Entering personal details pages - 1.5 hours Made minor changes in user story as discussed in previous meeting - 1.5 hours Discussion with team and Meeting with rafi - 3hours | Share feature in protoype - holded | 7 | 1 | Having doubt in creation for prototype of share feature
Kishore | Creation of prototype for Viewing their profiles | Requirement Refining- Break information for experience -1hr Prototypes for Login,Dashboard,Objective and Skills-2hrs Meeting with Rafi-1hr Meeting with Team Regarding Work assigning-2hrs | Profile Tempalte View | 6 | 1 | not having any idea how Profile template looks like
Nagaraj | Acceptance criteria for Admin | Acceptance criteria for Creator and Searcher - 2 hours Team Discussion on MoM scoped requirements-2 hours Meeting with raffi - 1 hour Hierarchy mapping - 30 minutes | - | 5.5 | 1 | -
Ramakrishna | Creation of prototype for Viewing their profiles | Requirement Refining- Profile details-1hr,Prototypes for Register,Education,Objective and Skills-2hrs,Meeting with Rafi-1hr,Meeting with Team Regarding Work assigning and Changes-2hrs | Profile Template while downloading and view | 6 | 1 | not having any idea how Profile template looks like
Sekhar | Exploring on Entity Framework. | Discussion and meeting with rafi - 1 hrs. Minor changes in user story and workflow - 1:30 hrs. Added admin as an another user, created admin workflow - 1 hrs. Discussion with team members - 2 hrs. | profile searcher can review another user profile. | 5:30 hrs | 1:30 hrs | Whether profile searcher or admin can review others profile.
Yoga Dharshini G | Admin controls and user profile reviews | Added admin as another user,created admin user story - 1:30hrs Made minor changes in user story and work flow - 2hr Discussion with Rafi - 1:30hrs Discussion with team members and Sekhar - 1:30 hr | Admin's other controls and Profile searcher or admin should review profiles or not | 6:30 Hrs | 3 hrs | Stuck with admin's other control flow and validation or verification has to be done or not

## 07-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Brindha | Exploration on Web API | Prototype for home page - 2 hours Acceptance criteria for Admin and HR - 1 hour Meeting with Raffi - 1.5 hour Team discussion - 2 hours | - | 6.5 | 1 | Practice with Balsamiq.
Chitrarasu | Exploration on WPI | Create prototype for view the created Profile - 2hrs Meeting with rafi - 1.5hr Discussion with Team about Prototype and admin user story - 3hrs | - | 6.5 | 1 | Practice with Balsamiq.
Dinesh Kumar | AB | AB | AB | AB | AB | AB
Gugan | Exploration on Entity Framework | Meeting with Rafi - 1.5 hrs Discussion with team about Prototype and admin user story - 3 hrs Prototype for HR user creation - 30 mins Prototype for Profile searcher view - 1.5hr | sharing profile,status | 6.5 | 1 | Doubt in share feature and status feature
Harini R | Exploration on web api | Created prototype for create profile page and home page - 2.5hrs Meeting with rafi - 1.5hr Discussion with Team about Prototype and admin user story - 3hrs | - | 7 | 1 | Doubt in share feature
Kishore | Entity Framework-Code first approach | Prototypes for Change Password and My profile-2hrs Meeting with Rafi-1hr Meeting with Team Regarding Work assigning-2hrs |  | 5 | 2
Nagaraj | - | Prototype for Login page - 30 mins Acceptance criteria for Admin and HR - 1 hour Meeting with Raffi - 1.5 hour Team discussion - 2.5 hours | - | 5.5 | 2 | Practiced with Balsamiq.
Ramakrishna | Entity Framework-Code first approach | Created prototypes for profile searcher view and HR user creation-2hrs,Meeting with Rafi-1.5hrs,Meeting with team regarding work assingnig and prototype designing-3hrs | sharing profile | 6.5 | 1 | Doubt in share feature and status feature
Sekhar | Exploration on Web API | Meeting with rafi - 1hr. Discussion with team member about prototype designing - 3hrs. Made changes in userstory (Creater,Searcher) & Created Admin, HR Partner userstory - 2hrs. | - | 6 | 1:30 | -
Yoga Dharshini G | Exploring prototype and Entityframework | Made changes in workflow (Creater,Searcher) & Created Admin, HR Partner workflow - 3hrs Discussion with team members - 2hrs Review with Rafi - 1:30hrs MOM updated and discussed - 1hr | Mail System | 7:30 | 2 | No clarification in mail system and share feature